## Cover
dittrichhudsonvasetti a r c h i t e c t s
COLEFORD CLOCK TOWER, COLEFORD, FOREST OF DEAN
RESTORATION AND REPARATION PROJECT 2026
PRELIMINARIES & SCHEDULE OF WORKS
June 2026
Dittrich Hudson Vasetti Architects is the trading name of Dittrich Hudson Architects Limited | Registered in England, company no. 7194499
Registered address: 5th Floor, Mariner House, 62 Prince Street, Bristol, BS1 4QD | VAT number: 184757758
Studios 12 - 14
9 Bath Buildings
Bristol BS6 5PT 0117 914 8317
info@dhva.co.uk
www.dhva.co.uk

## A - Prelims
SECTION A - GENERAL CONDITIONS & PRELIMINARIES | [5 empty] | Cost excl VAT (£)
A10 | PROJECT PARTICULARS
A10/110 | THE PROJECT:
Name: Coleford Clock Tower Restoration and Reparation Project 2026
Nature: Internal and external repairs and alterations
Location: Coleford Clock Tower, Market Place, Coleford, Gloucestershire GL16 8AW
Length of Contract: Approx 9 months
A10/120 | CLIENT:
Name: Laura-Jade Schroeder, Town Clerk and RFO, Coleford Town Council, 4 Mushet Walk, Coleford, Gloucestershire, GL16 8BQ
Address:
Telephone: 01594 832103
Email: ctcoffice@colefordtowncouncil.gov.uk
A10/127 | THE PRINCIPAL CONTRACTOR: The Contractor
A10/140 | ARCHITECT, CONTRACT ADMINISTRATOR (CA) & PRINCIPAL DESIGNER (hereinafter referred to as 'CA'):
Address: Dittrich Hudson Vasetti Architects, Studios 12-14, 9 Bath Buildings, Montpelier, Bristol BS6 5PT
Telephone: 0117 914 8317
Name: Oliver Forsyth (07528 366274)
Email: oliver@dhva.co.uk
A11 | INFORMATION
A11/110 | THE TENDER DRAWINGS are:
Architect's drawings:-
(Electronic only) |  | 1398 (00)01 |  | Site Location and Block Plans as Existing and Proposed
(Electronic only) |  | 1398 (00)02 |  | Main Contractor's Working Areas and Temporary Works
(Electronic only) |  | 1398 (10)01 |  | Floor Plans as Existing
(Electronic only) |  | 1398 (10)02 |  | Floor Plans as Proposed
(Electronic only) |  | 1398 (13)01 |  | Reflected Ceiling Plans as Proposed
(Electronic only) |  | 1398 (20)01 |  | Elevations as Existing
(Electronic only) |  | 1398 (20)02 |  | Elevations as Proposed (Sheet 1 of 2)
(Electronic only) |  | 1398 (20)03 |  | Elevations as Proposed (Sheet 2 of 2)
(Electronic only) |  | 1398 (22)01 |  | Internal Repair Elevations - Ground Floor
(Electronic only) |  | 1398 (22)02 |  | Internal Repair Elevations - First Floor
(Electronic only) |  | 1398 (22)03 |  | Internal Repair Elevations - Second Floor
(Electronic only) |  | 1398 (30)01 |  | Sections as Existing
(Electronic only) |  | 1398 (30)02 |  | Sections as Proposed
(Electronic only) |  | 1398 (30)03 |  | Lead Stepped Gutter Sections as Existing and Proposed
(Electronic only) |  | 1398 (40)01 |  | Ground Level Details as Proposed
(Electronic only) |  | 1398 (40)02 |  | First Floor Level Details as Proposed
(Electronic only) |  | 1398 (40)03 |  | Second Floor Level Details as Proposed
(Electronic only) |  | 1398 (40)04 |  | Roof Level Details as Proposed
(Electronic only) |  | 1398 (50)01 |  | Internal and External Windows, Doors and Hatches Schedule
(Electronic only) |  | 1398 (50)02 |  | Internal Stair and Handrail Schedule
(Electronic only) |  | 1398 (50)03 |  | Internal Joinery Schedule
(Electronic only) |  | 1203 (50)04 |  | Rainwater Drainage Schedule
Structural Engineer's drawings:-
(Electronic only) |  | 11954 010 T1 |  | Specification Notes
(Electronic only) |  | 11954 101 T1 |  | Repair Details Sheet 1
(Electronic only) |  | 11954 102 T1 |  | Repair Details Sheet 2
Scaffold design drawings:-
(Electronic only) |  | 26-TAD-039-DRG-001 |  | Plan Layout(s) Sheet 1
(Electronic only) |  | 26-TAD-039-DRG-002 |  | Plan Layout(s) Sheet 2
(Electronic only) |  | 26-TAD-039-DRG-003 |  | Access Scaffold Option 1
A11/121 | THE CONTRACT DOCUMENTS will be the tender drawings plus the following:
| - | Luminaires Schedule
| - | Priced Activity Schedule
| - | Specification
A11/160 | THE PRE-TENDER HEALTH AND SAFETY INFORMATION is included in these preliminaries in Section A34. It refers to information given in the preliminaries, specification and drawings.
A12 | THE SITE/EXISTING BUILDINGS
A12/110 | THE SITE:
Coleford Clock Tower, Market Place, Coleford, Gloucestershire GL16 8AW
A12/140 | EXISTING MAINS/SERVICES:
Single phase 230V electricity is available in the church free to use. Power on site can be connected to sockets located in the tower; this is free to use but the contractor is to ensure that adequate power is available and is safe to connect to, particularly for the hoist.
A12/170 | SITE INVESTIGATION:
No opening-up has been undertaken other than a visual survey inspection of the floor structures and the roof. Monitoring of the crack in the ceiling above the internal stair has been undertaken and no further action is needed at this stage.
A12/171 | SITE INVESTIGATION:
| Because of the external and high access level nature of the works, an asbestos survey of the areas affected has not been undertaken. A survey of the roof and internal ceiling areas will need to be undertaken at the outset of contract. Allow a PROVISIONAL SUM for undertaking an Asbestos Demolition and Refurbishment survey. |  |  |  |  | 750
A12/220 | ACCESS TO THE SITE:
All site visits at tender stage are to be arranged through the Architect.
The tower is to be kept locked at all times, and access to the upper floors and roof is only possible by internal ladder and narrow stair access.
A12/210 | PARKING:
There is no available parking on site and a Highways License will need to be obtained for partial possession of Market Place. Deliveries will need to be unloaded on the edge of Market Place and there will be vehicle weight restrictions in place to avoid damage to the existing paved surfaces. Separate parking is available at the Contractor's expense, and is located nearby at Railway Drive.
A12/220 | USE OF THE SITE:
Do not use the site for any other purpose other than carrying out the works.
A12/240 | RISKS TO HEALTH AND SAFETY:
| - | A full pre-contract risk register is included in section A34.
| - | The site is located in the town centre with significant vehicular movement and traffic around Market Place. Loading arrangements, parking suspensions and provisions for moving materials safely will need to be in place.
| - | Safety for members of the public will need to be considered at all times; part of the public areas around the base of the tower will need to be closed off to form the site compound and temporary segregation arrangements will need to be put in place for the safe management of pedestrians at all times.
A12/280 | SITE VISIT: Before tendering, ascertain the nature of the site, access thereto and all local conditions and restrictions likely to affect the execution of the Works.
A12/290 | SITE VISIT may be made during normal working hours, Monday to Friday. Inform the client representative as A10/140 ahead of visiting.
A20 | JCT INTERMEDIATE BUILDING CONTRACT ICD 2024
CONTRACT
The form of contract will be the JCT ICD 2024 – Intermediate Building Contract with Contractor Design with all current revisions. Allow for the obligations, liabilities and services described therein against the headings below.
The Contract is to be executed under hand.
ARTICLES OF AGREEMENT
| The Employer: |  | Coleford Town Council
| The Contractor: |  | To be determined
RECITALS
| First Recital: |  | Internal and external repairs and alterations at Coleford Clock Tower, Market Place, Coleford.
| Second Recital: |  | "Specialist access and electrical installations throughout".
| Third Recital: |  | “the Contract Drawings” - section A11/110 as the Contract Preliminaries.
| Fourth Recital: |  | “the Bills of Quantities” to be deleted. "the Work Schedules" to be deleted and replaced with "Priced Activity Schedule".
| Fifth Recital: |  | (A) "Bills of Quantities" to be deleted. Pricing option (B) to be deleted.
| Sixth Recital: |  | Applies.
| Seventh Recital: |  | Applies.
| Eighth Recital: |  | The client is not a contractor for the purposes of the Construction Industry Scheme.
| Ninth Recital: |  | Delete.
| Tenth Recital: |  | The Construction (Design and Management) Regulations 2015 apply.
| Eleventh Recital: |  | Applies and delete "the Bills of Quantities".
| Twelfth Recital: |  | Delete.
| Thirteenth Recital: |  | Supplemental provisions 1, 2 and 3 applies.
ARTICLES
| Article 1: |  | The Contractor’s obligations are as set out in the contract.
| Article 2: |  | The Contract Sum - shall be defined as accepted.
| Article 3: |  | Collaborative working applies.
| Article 4: |  | The term ‘Architect/ Contract Administrator’ in the conditions shall mean DHV Architects.
| Article 5: |  | The term ‘Quantity Surveyor’ in the conditions for the contract administration and valuations shall mean DHV Architects. The tender sum analysis and final account will be prepared by DHV Architects.
| Article 6: |  | For the purposes of the CDM Regulations the term 'Principal Designer' shall mean DHV Architects. The 'Principal Contractor' shall mean the Main Contractor and TBC.
| Article 7: |  | For the purposes of the Building Regulations the term 'Principal Designer' shall mean DHV Architects. The 'Principal Contractor' shall mean the Main Contractor and TBC.
| Article 8: |  | Adjudication applies as clause 9.3.
| Article 9: |  | Arbitration does not apply.
| Article 10: |  | Legal proceedings; dispute or difference applies.
CONTRACT PARTICULARS: GENERAL PART 1
Fourth Recital: To instruct the Contractor to carry out the works in accordance with the contract documentation and contract.
Sixth Recital: To carry out the works in accordance with the Employer's instructions, contract documents and the contract. CDP analysis does not apply.
Eighth Recital and clause 4.6: The employer is not a contractor.
Tenth Recital: The project is notifiable under the CDM Regulations.
Eleventh Recital: "Works Schedules" to be replaced with "Priced Activity Schedule".
Twelfth Recital: To be deleted - there is no framework agreement.
Thirteenth Recital and Schedule 4:
Supplemental Provision 1: Health and Safety - applies.
Supplemental Provision 2: Cost savings and value improvements - applies.
Supplemental Provision 3: Performance indicators and monitoring - applies.
Article 9: Arbitration - Does no apply
| 1.1 | The Base Date is 10 days prior to the date of the return of tenders.
| 1.1 | BIM Protocol does not apply.
| 1.1 | Date for Completion: TBA and sectional completion does not apply.
| 1.7.3 | Employer address for service of notices: Coleford Town Council, 4 Mushet Place, Coleford GL16 8BQ.
Contractor address for service of notices: TBA.
The respective email address for the Employer is: ctcoffice@colefordtowncouncil.gov.uk
The respective email address for the Contractor is: TBA.
| 1.7.4.2 | Does not apply.
| 2.4 | Date of Possession of the site: TBA. Sectional possession does not apply.
| 2.5 | Deferment of possession of the site does not apply.
| 2.23.2 | Liquidated Damages; £250.00/working day. Sectional liquidated damages do not apply.
| 2.29 | Does not apply.
| 2.30 | Rectification Period: 12 months. Sectional rectification periods do not apply.
| 2.34.3 | Contractor's Designed Portion: limit of Contractor's liability for loss of use etc.: TBA.
| 4.3 and 4.9 | Fluctuations: do not apply.
| 4.7 | Advance payments and advance payment bonds do not apply.
| 4.8.1 | Interim payments - Interim Valuation Dates: At monthly intervals and one month from possession of the site.
| 4.9.1 | Interim payments - 95% to Practical Completion; 97.5% thereafter Practical Completion.
| 4.10.4 | Listed items - does not apply.
| 4.10.5 | Listed items - does not apply.
| 4.17.5 and 4.17.6 | Relevant matters: applies.
| 6.4.1 | Contractor’s Public Liability Insurance: £5,000,000 minimum level of covered required.
| 6.5.1 | Employer's Liability Insurance: Does not apply.
| 6.7 and Schedule 1 | Works insurance - Insurance Option C applies (joint names insurance by the Employer).
Percentage to cover professional fees does not apply.
Insurance Option A does not apply.
Insurance Option C applies where the building is existing.
| 6.1 and Schedule 1 | Terrorism Cover is not required.
| 6.15 | The Joint Fire Code applies. The work is not a large project.
| 6.18 | The Joint Fire Code applies. The cost of amendments shall be borne by the contractor.
| 6.19 | Contractor's Designed Portion Professional Indemnity Insurance: TBA.
| 7.2.1 | A performance bond is not required.
| 7.2.2 | A parent company guarantee is not required.
| 7.3 | Collateral warranties are not required.
| 8.9.2 etc. | Period of suspension is two months as the default position.
| 9.1 | Notification and negotiation of disputes:
Employer's nominee: Laura-Jade Schroeder, Town Clerk and RFO.
Contractor's nominee: TBA (Managing Director).
| 9.3.1 | Adjudication: Royal Institute of British Architects is the nominated Adjudicator.
| 9.5.1 | Arbitration: does not apply.
ATTESTATION
Contract is to be executed under hand.
A30 | TENDERING/SUBLETTING/SUPPLY
MAIN CONTRACT TENDERING
A30/110 | SCOPE: These conditions are supplementary to those in the invitation to tender and on the Form of Tender.
A30/121 | TENDERING PROCEDURE will be in accordance with the principles of the JCT Practice Note 6 (Series 2) except as follows:
The two lowest pricing contractors will be shortlisted for assessment. Assessment will be on lowest cost (60%) and methodology; proposed site staff experience; demonstration of quality control and approach to the project (40%). Scoring criteria will be released during the tender period.
A30/160 | EXCLUSIONS: If the Contractor cannot tender for any part(s) of the work as defined in the tender documents they must inform the Architect as soon as possible, defining the relevant part(s) and stating the reason(s) for their inability to tender.
A30/170 | ACCEPTANCE OF TENDER: The Employer and representatives:
| - | Offer no guarantee that the lowest or any tender will be recommended for acceptance or accepted.
| - | Will not be responsible for any cost incurred in the preparation of any tender.
A30/190 | PERIOD OF VALIDITY: Tenders must remain open for consideration (unless previously withdrawn) for not less than 90 days from the date fixed for the submission or lodgement of tenders. Information on the date for possession/commencement is given in section A20.
PRICING/ SUBMISSION OF DOCUMENTS
A30/211 | PRELIMINARIES IN THE SPECIFICATION: The Preliminaries/General conditions sections (A10-A55 inclusive) must not be relied on as complying with SMM7.
A30/220 | PRICING OF PRELIMINARIES: The following abbreviations have been used:
|  | F | = | Fixed charge item
|  | TR | = | Time related charge item.
A30/240 | PRICING OF PERFORMANCE SPECIFIED WORK:
| - | Tenders must include for all associated and ancillary work shown or clearly apparent as being necessary to meet the requirements for the Performance Specified Work and its completion and proper integration with the Works generally.
| - | Tenderers must price on the work and quantities which they intend to provide and will be responsible for any error therein. Where provided, quantities are indicative only.
A30/250 | PRICING DOCUMENTS:
| - | Alterations to the pricing documents must not be made without the written consent of the Architect. Tenders containing unauthorised alterations or qualifications may be rejected.
| - | The work shown on the drawings, the specification, and in the Schedule of Works is to be priced. Where discrepancies or omissions arise, the work shown in the drawings and specifications is to take precedence.
| - | Costs relating to items which are shown or are implicit to deliver the work shown on the drawings and in the specification will be deemed to have been included.
A30/310 | SPECIFICATION WITHOUT QUANTITIES: Where and to the extent that quantities are not included in the specification, tenders must include for all work shown or described in the tender documents as a whole or clearly apparent as being necessary for the complete and proper execution of the Works.
A30/360 | THE PRICED SCHEDULE OF WORKS must be submitted as part of the tender.
A30/440 | SCHEDULE OF RATES: N/A other than where requested in the Dayworks section.
A30/510 | ALTERNATIVE METHOD TENDERS:
| - | In addition to and at the same time as their tender for the Works as defined in the tender documents, the Contractor may, at their discretion, submit alternative method(s) of construction for consideration. Alternatives which would involve significant changes to other work will not be considered.
| - | Such alternative(s) will be deemed to be alternative tender(s) and each must include a complete and precise statement of the effects on cost and programme.
| - | Carry out a health and safety risk assessment for each such alternative and where appropriate provide a safety method statement suitable for incorporation in the Health and Safety Plan.
A30/535 | SUBSTITUTE PRODUCTS: If the Contractor wishes to substitute products of different manufacture to those specified, details must be submitted with the tender giving reasons for each proposed substitution. substitutions which have not been notified at tender stage may not be considered. Substitutions sanctioned by the CA will be subject to the verification requirements of clause A31/200.
A30/540 | QUALITY CONTROL RESOURCES: A statement must be submitted with the tender describing the organisation and resources which the Contractor proposes and undertakes to provide to control the quality of the Works, including the work of subcontractors. The statement must include the number and type of staff responsible for quality control, with details of their qualifications and duties.
A30/570 | CONSTRUCTION PHASE HEALTH AND SAFETY PLAN must be submitted by the appointed contractor one week before commencement of work on site and is to include the following:
| - | Method statements related to the construction hazards identified in the pre-tender health and safety plan and/or statements on how the hazards will be addressed and other significant hazards identified by the contractor.
| - | Details of the management structure and responsibilities.
| - | Arrangements for issuing health and safety directions.
| - | Procedures for informing other contractors and employees of health and safety hazards.
| - | Selection procedures for ensuring competency of other contractors, the self-employed and designers.
| - | Procedures for communications between the project team, other contractors and site operatives.
| - | Arrangements for co-operation and co-ordination between contractors.
| - | Procedures for carrying out risk assessment and for managing and controlling the risk.
| - | Emergency procedures including those for fire prevention and escape.
| - | Arrangements for ensuring that all accidents, illness and dangerous occurrences are recorded.
| - | Arrangements for welfare facilities.
| - | Procedures for ensuring that all persons on site have received relevant health and safety information and any training.
| - | Arrangements for preparing site rules and drawing them to the attention of those affected and ensuring their compliance.
| - | Monitoring procedures to ensure compliance with site rules, selection and management procedures, health and safety standards and statutory requirements.
SUBLETTING/SUPPLY
A30/632 | DOMESTIC SUBCONTRACTS: Comply with the Construction Industry Board 'Code of practice for the selection of subcontractors', April 1997.
A30/640 | DOMESTIC SUBCONTRACTORS - the contractor is free to use sub-contractors as seen fit, although a statement outlining the sub-contractor's approach and relevant experience to the project will be required, and it the statement or experience are not deemed satisfactory by the client and architect the contract may not be let. This is to ensue that standards of cleanliness, cooperation, quality and timing meet the client's requirements.
A30/641 | DOMESTIC SUBCONTRACTORS:
| - | If the Contractor wishes to add additional person(s) to any list given under the provisions of Contract clause 19.3, they must apply in writing to the CA and, if requested, submit to the CA (in an approved form) evidence of the suitability of such additional person(s). Wherever possible, submissions for addition of person(s) must be made, and consent obtained, before return of the tender. When any submission for addition of person(s) is made with the tender the consequences, if any, to the tender price compared to the use of the listed persons are to be made clear or the tender will be treated as qualified.
| - | Before the start of the work to which the list relates, the Contractor must enter into a binding subcontract agreement and confirm to the CA that this has been done, giving the name of the selected subcontractor.
A31 | PROVISION, CONTENT AND USE OF DOCUMENTS
DEFINITIONS AND INTERPRETATIONS
A31/110 | DEFINITIONS
Meaning: Terms, derived terms and synonyms used in the preliminaries/general conditions and the specification are as stated therein or in the appropriate British Standard or British Standard Glossary.
A31/120 | COMMUNICATION:
Definition: Includes advise, inform, submit, give notice, instruct, agree, confirm, seek or obtain information, consents or instructions, or make arrangements.
Format: In writing to the person named in the clause A10/140 unless specified otherwise.
Response: Do not proceed until response has been received.
A31/141 | DRAWINGS:
Definitions: To BSRIA technical note BG 6 'A Design Framework for Building Services'
A31/161 | TERMS USED IN SPECIFICATION:
Remove: disconnect, dismantle as necessary and take out the designated products or work and associated accessories, fixings, supports, linings and bedding materials. Dispose of unwanted materials. Excludes taking out and disposing of associated pipework, wiring, duct work or other services.
Fix: Unload, handle, store, place and fasten in position including all labours and use of site equipment.
Supply and fix: includes all labour and site equipment for unloading, handling, storing and executions. All products to be supplied and fixed unless stated otherwise.
Keep for reuse: Do not damage designated products or works. Clean off bedding and jointing materials. Stack neatly, adequately protect and store until required by the employer or for use in the works as instructed.
Make good: Execute local remedial work to designated work. Make secure, sound and neat. Excludes redecoration and/or replacement.
Renew: Supply and fix new products matching those removed. Execute work to match original new state of that removed.
Repair: Execute remedial work to designated products. Make secure, sound and neat excludes redecoration and/or replacement.
Refix: Fix removed products.
Ease: Adjust moving parts of designated products or work to achieve free movement and good fit in open and closed positions.
Match existing: Provide products and work of the same appearance and features as the original, excluding aging and weathering. Make joints between existing and new work as inconspicuous as possible.
System: Equipment, accessories, control, supports and ancillary items, including installation, necessary for that section of the work to function.
A31/170 | MANUFACTURER AND PRODUCT REFERENCE
Definition: When used in this combination:
Manufacturer: The firm under whose name the particular product is marketed. Product reference: The proprietary brand name and/or reference by which the particular product is identified.
Currency: References are to the particular product as specified in the manufacturers’ technical literature current on the date of the invitation to tender.
A31/220 | REFERENCED DOCUMENTS:
- | Drawings and specification prevail over referenced documents.
A31/250 | CURRENCY OF DOCUMENTS:
- | References to published documents are to the editions including amendments and revisions current on the date of the invitation to tender.
DOCUMENTS PROVIDED ON BEHALF OF EMPLOYER
A31/411 | ADDITIONAL COPIES OF DRAWINGS:
Two copies of drawings (not counting any certified copy of the Contract Drawings) will be issued free of charge. Additional copies will be issued on request but will be charged to the Contractor. Electronic copies will be readily distributed.
A31/440 | DIMENSIONS:
Scaled dimensions: do not rely on for construction.
A31/509 | COPYRIGHT:
All tender documents and drawings, specifications and schedules are the copyright of DHVA.
A31/510 | CONTRACTORS DESIGN DOCUMENTS:
Master programme: Make reasonable allowance for completing design/production information, submission (including to the CDM Principal Designer) comment, inspection, amendment, resubmission and re-inspection.
A31/600 | CONTRACTORS DESIGN INFORMATION
Contractors designed work: Include: Specialist access and electrical installation designs.
A31/620 | AS BUILT DRAWINGS AND INFORMATION
Contractor designed work: Provide drawings/information:
Submit: At least 2 weeks before date of completion.
A31/630 | TECHNICAL LITERATURE:
Information: Keep on site for reference by all supervisory personnel.
A32 | MANAGEMENT OF THE WORKS
GENERALLY
A32/110 | SUPERVISION: Accept responsibility for co-ordination, supervision and administration of the Works, including all subcontracts. Arrange and monitor a programme with each subcontractor, supplier, local authority and statutory undertaker, and obtain and supply information as necessary for co-ordination of the work.
A32/120 | INSURANCE: Before starting work on site submit documentary evidence and/or policies and receipts for the insurance required by the Conditions of Contract.
A32/130 | INSURANCE CLAIMS: If any event occurs which may give rise to any claim or proceeding in respect of loss or damage to the Works or injury or damage to persons or property arising out of the Works, forthwith give notice in writing to the Employer, the CA and the Insurers. Indemnify the Employer against any loss which may be caused by failure to give such notice.
A32/140 | CLIMATIC CONDITIONS: Keep an accurate record of:
| - | Daily maximum and minimum air temperatures (including overnight).
| - | Delays due to adverse weather, including description of the weather, type(s) of work affected and number of hours lost.
A32/150 | OWNERSHIP: Materials arising from the work are to become the property of the Contractor except where otherwise stated. Remove from site as work proceeds.
PROGRAMME/ PROGRESS
A32/210 | PROGRAMME:
| - | The master programme for the Works must make allowance for:
|  | - | Design, production information and proposals provided by the Contractor/Subcontractors/Suppliers, including inspection and checking (see section A31).
|  | - | Planning and mobilisation by the Contractor.
|  | - | Running in, adjustment, commissioning and testing of all engineering, building services and installations.
|  | - | Work resulting from instructions issued in regard to the expenditure of provisional sums (see section A54).
|  | - | Work by or on behalf of the Employer and concurrent with the Contract (see section A50) the nature and scope of which, the relationship with preceding and following work and any relevant limitations are suitably defined in the Contract Documents.
|  | - | Where and to the extent that the programme implications for work which is not so defined are impossible to assess the Contractor should exclude it from his programme and confirm this when submitting the programme.
A32/211 | HOURS OF WORKING, RESTRICTIONS & SERVICES
| - | There are restrictions on working on site as follows:
|  | - | The tower is located in the town centre and the site is to be kept secure to prevent members of the public from accessing the site at all times. The permitted working hours are Monday to Friday, 8am-6pm and no weekend working is allowed unless otherwise agreed with the CA.
A32/212 | PROGRAMME:
| - | As soon as possible and before starting work on site prepare in an approved form a master programme for the Works, which must make allowance for:
|  | - | Design and production information provided by the Contractor/Subcontractors/Suppliers, including inspection and checking (see section A31).
|  | - | Planning and mobilisation by the Contractor.
|  | - | Work resulting from instructions issued in regard to the expenditure of provisional sums (see section A54).
|  | - | Work by or on behalf of the Employer and concurrent with the Contract (see section A50) the nature and scope of which, the relationship with preceding and following work and any relevant limitations are suitably defined in the Contract Documents.
|  | - | Where and to the extent that the programme implications for work which is not so defined are impossible to assess the Contractor should exclude it from his programme and confirm this when submitting the programme.
A32/230 | SUBMISSION of programmes will not relieve the Contractor of their responsibility to advise the CA of the need for further drawings or details or instructions in accordance with Clause 5.4.2 of the Conditions of Contract.
A32/250 | MONITORING: Record progress on a copy of the programme to be kept on site. If any circumstances arise which may affect the progress of the Works put forward proposals or take other action as appropriate to minimise any delay and to recover any lost time.
A32/260 | ARCHITECT SITE MEETINGS:
| - | The Architect will hold a monthly site inspection to review progress and other matters arising from the administration of the Contract.
| - | Attend all meetings and inform subcontractors and suppliers when their presence is required.
| - | The Architect will chair the meetings and take and distribute record notes and actions.
A32/280 | PHOTOGRAPHS: Take regular digital photographs of work progressing to form a conservation record. Provide a digital file at completion of the project with photographs catalogued by area and date and to be shared with the Employer and CA.
A32/290 | NOTICE OF COMPLETION: Give Architect and Employer at least 1 week notice of the anticipated date of Practical Completion.
A32/300 | ADVERSE WEATHER: Use all reasonable and suitable building aids and methods to prevent or minimise delays during adverse weather conditions.
CONTROL OF COST
A32/420 | EXISTING WORK: The extent and location of renewal of existing work must be agreed before the work is started. Remove existing work in ways which will reasonably minimise the amount of removal and renewal.
A32/460 | INTERIM VALUATIONS: At least 7 days before the end of each established Period for interim valuations (the Due Date) submit to the Architect details of amounts due under the Contract together with all necessary supporting information.
A32/470 | UNFIXED MATERIALS: Payment for materials and goods off-site will not be made until such goods have been fixed.
A33 | QUALITY STANDARDS/CONTROL
MATERIALS AND WORK GENERALLY
A33/110 | GOOD PRACTICE: Where and to the extent that materials, products and workmanship are not fully detailed or specified they are to be:
| - | Of a standard appropriate to the Works and suitable for the functions stated in or reasonably to be inferred from the project documents, and:
| - | In accordance with relevant good building practice.
| - | Contract Documents: Omissions or errors in description and/ or quantity shall not vitiate the Contract nor release the Contractor from any obligations or liabilities under the Contract.
A33/115 | GOOD PRACTICE:
| - | All work to be in accordance with BS 7913:2013 The Principles of the Conservation of Historic Buildings.
A33/120 | GENERAL QUALITY OF PRODUCTS:
| - | Products to be new unless otherwise specified.
| - | For products specified to a British or European Standard obtain certificates of compliance from manufacturers when requested by the CA.
| - | Where a choice of manufacturer or source of supply is allowed for any particular product, the whole quantity required to complete the work must be of the same type, manufacture and/or source unless otherwise approved. Produce written evidence of sources of supply when requested by the CA.
| - | Ensure that the whole quantity of each product required to complete the work is of consistent of the same kind, size, quality and overall appearance.
| - | Where consistency of appearance is desirable ensure consistency of supply from the same source. Unless otherwise approved, do not use different colour batches where they can be seen together.
| - | If products are prone to deterioration or have a limited shelf life, order in suitable quantities to a programme and use in appropriate sequence. Do not use if there are any signs of deterioration, setting or other unsatisfactory condition.
A33/130 | PROPRIETARY PRODUCTS:
| - | Handle, store, prepare and use or fix each product in accordance with its manufacturer's current printed or written recommendations/instructions. Inform CA if these conflict with any other specified requirement. Submit copies to the CA when requested.
| - | The tender will be deemed to be based on the products specified and recommendations on their use as described in the manufacturer's literature current at the date of issue of the tender information to the Contractor.
| - | Obtain confirmation from manufacturers that the products specified and recommendations on their use have not been changed since that time. Where such change has occurred, inform the CA and do not place orders for or use the affected products without further instructions.
| - | Where British Board of Agrement certified products are used, comply with the limitations, recommendations and requirements of the relevant valid certificates.
A33/140 | CHECKING COMPLIANCE OF PRODUCTS: Check all delivery tickets, labels, identification marks and, where appropriate, the products themselves to ensure that all products comply with the project documents. Where different types of any product are specified, check to ensure that the correct type is being used in each location. In particular, check that:
| - | The sources, types, qualities, finishes and colours are correct, and match any approved samples.
| - | All accessories and fixings which should be supplied with the goods have been supplied.
| - | Sizes and dimensions are correct. Where tolerances of components are critical, measure a sufficient quantity to ensure compliance.
| - | The delivered quantities are correct, to ensure that shortages do not cause delays in the work.
| - | The products are clean, undamaged and otherwise in good condition.
| - | Products which have a limited shelf life are not out of date.
A33/150 | PROTECTION OF PRODUCTS:
| - | Prevent over-stressing, distortion and any other type of physical damage.
| - | Keep clean and free from contamination. Prevent staining, chipping, scratching or other disfigurement, particularly of products exposed to view in the finished work.
| - | Keep dry and in a suitably low humidity atmosphere to prevent premature setting, moisture movement and similar defects. Where appropriate store off the ground and allow free air movement around and between stored products.
| - | Prevent excessively high or low temperatures and rapid changes of temperature in the products.
| - | Protect adequately from rain, damp, frost, sun and other elements as appropriate. Ensure that products are at a suitable temperature and moisture content at time of use.
| - | Ensure that sheds and covers are of ample size, in good weatherproof condition and well secured.
| - | Keep different types and grades of products separately and adequately identified.
| - | So far as possible, keep products in their original wrappings, packings or containers, until immediately before they are used.
| - | Wherever possible retain protective wrappings after fixing and until shortly before Practical Completion.
| - | Ensure that protective measures are fully compatible with and not prejudicial to the products/materials.
A33/160 | SUITABILITY OF RELATED WORK AND CONDITIONS: Ensure that all trades are provided with necessary details of related types of work. Before starting each new type or section of work, ensure that:
| - | Previous, related work is appropriately complete, in accordance with the project documents, to a suitable standard and in a suitable condition to receive the new work.
| - | All necessary preparatory work has been carried out, including provision for services, openings, supports, fixings, damp proofing, priming and sealing.
| - | The environmental conditions are suitable, particularly that the building is suitably weathertight when internal components, services and finishes are installed.
A33/170 | GENERAL QUALITY OF WORKMANSHIP:
| - | Operatives must be appropriately skilled and experienced for the type and quality of work.
| - | Take all necessary precautions to prevent damage to the work from frost, rain and other hazards. Work deemed to have been damaged by frost within 28 days of undertaking will be replaced by the Contractor where instructed by the CA at no cost to the Employer.
| - | Inspect components and products carefully before fixing or using and reject any which are defective.
| - | Fix or lay securely, accurately and in alignment.
| - | Where not specified otherwise, select fixing and jointing methods and types, sizes and spacings of fastenings in compliance with section Z20. Fastenings to comply with relevant British Standards.
| - | Provide suitable, tight packings at screwed and bolted fixing points to take up tolerances and prevent distortion. Do not overtighten fixings.
| - | Adjust location and fixing of components and products so that joints which are to be finished with mortar or sealant or otherwise left open to view are even and regular.
| - | Ensure that all moving parts operate properly and freely. Do not cut, grind or plane prefinished components and products to remedy binding or poor fit without approval.
A33/180 | BS 8000: BASIC WORKMANSHIP:
| - | Where compliance with BS 8000-0:2014 is specified, this is only to the extent that the recommendations therein define the quality of the finished work.
| - | Where BS 8000-0:2014 gives recommendations on particular working methods or other matters which are properly within the province and responsibility of the Contractor, compliance therewith will be deemed to be a matter of general industry good practice and not a specific requirement of the CA under the Contract.
| - | If there is any conflict or discrepancy between the recommendations of BS 8000-0:2014 on the one hand and the project documents on the other, the latter will prevail.
A33/190 | WATER FOR THE WORKS: Clean and uncontaminated. If other than mains supply is proposed provide evidence of suitability. Test to BS EN 1008:2002 if instructed.
SAMPLES/APPROVALS
A33/210 | APPROVAL OF PRODUCTS: Where approval of a product is specified the requirement for approval relates to a sample of the product and not to the product as used in the Works. Submit a sample or other evidence of suitability. Do not confirm orders or use the product until approval of the sample has been obtained. Retain approved sample in good, clean condition on site. Ensure that the product used in the Works matches the approved sample.
A33/220 | SAMPLES OF FINISHED WORK: Where a sample of finished work is specified for approval, the requirement for approval relates to the sample itself (if approval of the finished work as a whole is required this is specified separately). Obtain approval of the stated characteristic(s) of the sample before proceeding with the Works. Retain approved sample in good, clean condition on site. Ensure that the relevant characteristic(s) of the Works match the approved characteristic(s) of the sample. Remove samples which are not part of the finished Works when no longer required.
A33/230 | APPROVALS: Where and to the extent that products or work are specified to be approved or the CA instructs or requires that they are to be approved, the same must be supplied and executed to comply with all other requirements and in respect of the stated or implied characteristics either:
| - | To the express approval of the CA or:
| - | To match a sample expressly approved by the CA as a standard for the purpose.
A33/240 | APPROVALS: Inspection or any other action by the CA must not be taken as approval of products or work unless the CA so confirms in writing in express terms referring to:
| - | Date of inspection
| - | Part of the work inspected
| - | Respects or characteristics which are approved
| - | Extent and purpose of the approval
| - | Any associated conditions.
ACCURACY/SETTING OUT GENERALLY
A33/340 | APPEARANCE AND FIT:
| - | Arrange the setting out, erection, juxtaposition of components and application of finishes (working within the practical limits of the design and the specification) to ensure that there is satisfactory fit at junctions, that there are no practically or visually unacceptable changes in plane, line or level and that the finished work has a true and regular appearance.
| - | Wherever satisfactory accuracy, fit and/or appearance of the work are likely to be critical or difficult to achieve, obtain approval of proposals or of the appearance of the relevant aspects of the partially finished work as early as possible.
| - | Without prejudice to the above and unless specified otherwise, tolerances will (where applicable) be not greater than those given in BS 5606:2022, Tables 1 and 2.
SERVICES GENERALLY
A33/410 | SERVICES REGULATIONS: Any work carried out to or which affects new or existing services must be in accordance with the Bye Laws or Regulations of the relevant Statutory Authority.
A33/420 | SERVICE RUNS: Make adequate provision for services, including unobstructed routes and fixings. Wherever possible ducts, chases and holes are to be formed during construction rather than cut, unless otherwise stated. All highly visible service routes are to be coordinated to minimise any visual impact to the Grade II listed building and all works to be agreed with the CA before proceeding.
A33/440 | MECHANICAL AND ELECTRICAL SERVICES must have final tests and commissioning carried out so that they are in full working order at the completion of each Section.
SUPERVISION/INSPECTION/DEFECTIVE WORK
A33/510 | SUPERVISION: In addition to the constant management and supervision of the works provided by the Contractor's person in charge, all significant types of work must be under the close control of competent trade supervisors to ensure maintenance of satisfactory quality and progress.
A33/520 | PERSON-IN-CHARGE: Give maximum possible notice to the CA before changing the person-in-charge.
A33/550 | DEFECTS IN EXISTING CONSTRUCTION to be reported to the CA without delay. Obtain instructions before proceeding with work which may:
| - | Cover up or otherwise hinder access to the defective construction, or
| - | Be rendered abortive by the carrying out of remedial work.
A33/555 | ACCESS FOR INSPECTION: Give the CA not less than 1 week notice before removing scaffolding or other facilities for access.
A33/560 | TIMING OF TESTS AND INSPECTIONS: Agree dates and times of tests and inspections with the CA at least seven working days in advance, to enable the CA and other affected parties to be present. On the previous working day to each such test or inspection confirm that the work or sample in question will be ready or, if not ready, agree a new date and time.
A33/565 | TEST CERTIFICATES: Submit a copy of each certificate to the CA as soon as practicable and keep copies of all certificates on site.
A33/570 | PROPOSALS FOR RECTIFICATION OF DEFECTIVE WORK/PRODUCTS:
| - | As soon as possible after any part(s) of the work or any products are known to be not in accordance with the Contract or appear that they may not be in accordance, submit proposals to the CA for opening up, inspection, testing, making good, adjustment of the Contract Sum, or removal and re-execution.
| - | Such proposals may be unacceptable to the CA and he may issue contrary instructions.
A33/580 | MEASURES TO ESTABLISH ACCEPTABILITY: Wherever inspection or testing shows that the work, materials or goods are not in accordance with the Contract and measures (e.g. testing, opening up, experimental making good) are taken to help in establishing whether or not the work is acceptable, such measures:
| - | will be at the expense of the Contractor, and:
| - | will not be considered as grounds for extension of time.
A33/590 | QUALITY CONTROL: Establish and maintain procedures to ensure that the Works, including the work of all subcontractors, comply with specified requirements. Maintain full records, keep copies on site for inspection by the CA, and submit copies of particular parts of the records on request. The records must include:
| - | Identification of the element, item, batch or lot including location in the Works.
| - | The nature and dates of inspections by the Contractor or CA, tests and approvals.
| - | The nature and extent of any nonconforming work found.
| - | Details of any corrective action.
A34 | SECURITY/SAFETY/PROTECTION
GENERALLY
A34/110 | THE PRE-TENDER CONSTRUCTION INFORMATION is integral with the project Preliminaries, including but not restricted to the sections set out below.
Nature of the project: Sections A10 and A13.
The existing environment: Section A12.
Existing drawings: Sections A11 and A12.
The design: Section A34.
Construction materials: Section A34.
Site-wide elements: Section A12.
Overlap with client’s undertaking: Sections A34 and A36.
Site Rules: Sections A34 and A35.
Continuing liaison: Section A31.
A34/114 | CONSTRUCTION HAZARDS arising from the design of the project which the contractor should be aware of include those identified below. Common-place hazards (such as working with lime), which should be controlled by good management and good site practices, are not listed.
| 1 | Hazard: Falling from height
Precautions: To avoid the risk of falling a full scaffold to the main external working areas around the clock tower is required. The roofspace of the tower is open between the rafters, so secondary debris netting will need to be installed immediately below the underside of the rafters to prevent falling through the roof.
| 2 | Hazard: Protection of public
Precautions: The public are to be excluded from the area around the contractor's allocated working areas for the duration of work by the use of plywood hoarding around the perimeter of the site. Secondary protections are to be used to further deter trespassers from accessing the scaffold if the site is unlawfully entered. Scaffold access and erection will need to be undertaken from the adjoining highways surrounding Market Place and carried to their final positions by hand. The scaffold is to have a crash deck in areas where work is underway above any areas of pavement open to the public below.
| 3 | Hazard: Vehicle collisions and danger to pedestrians
Precautions: There is no parking for contractor's vehicles available at the site and the nearest point for vehicular access is opposite the end of the High Street on Market Place. Pedestrians access Market Place as it is a public thoroughfare. Particular care is to be taken while delivering materials and in all vehicle movements in and around the site with clear and necessary public segregations as required.
| 4 | Hazard: Dust and noise
Precautions: Dust is to be kept to an absolute minimum during the works. Drilling or sawing is to be undertaken under a vacuum nozzle or wetted down. Noise is to be managed at all times where the site is located in the town centre. Radios are not allowed on site. As such, noise restrictions are in place and are not to take place outside of the hours 8am-6pm, Monday to Friday. No weekend working is permitted unless otherwise agreed with the CA.
| 5 | Hazard: Public interaction & crime
Precautions: Some members of the public may try and interact with contractors outside the church or around the site. Disturbed or antisocial people (mainly street drinkers) and occasionally try to access the site and will need to be kept away from the works. People may try to climb the scaffold and steal lead; the scaffold perimeter is to be fully secured and all doors are to be kept locked at all times. The scaffold is to be alarmed. Site workers should be made aware of the procedures to assist such people or call for help from the police in extreme cases.
A34/120 | THE CONSTRUCTION PHASE HEALTH AND SAFETY PLAN must be submitted to the CA not less than 7 days before the proposed date for start of construction work. Do not start construction work until the CA has confirmed in writing that in his view the Construction Phase Health and Safety Plan includes the procedures and arrangements required by the CDM Regulations.
A34/125 | HSE APPROVED CODES OF PRACTICE: Comply with the following:
| - | Management of health and safety at work.
| - | Managing construction for health and safety.
A34/130 | SECURITY: Adequately safeguard the site, the Works, products, materials, plant, and any existing buildings affected by the Works from damage and theft. Take all reasonable precautions to prevent unauthorised access to the site, the Works and adjoining property.
A34/140 | STABILITY: Accept responsibility for the stability and structural integrity of the Works during the Contract, and support as necessary. Prevent overloading: details of design loads may be obtained from the CA.
A34/170 | EMPLOYER’S REPRESENTATIVES SITE VISITS:
| - | Inform the CA in advance of all safety provisions and procedures (including those relating to materials which may be deleterious) which will require the compliance of the Employer or their representatives when visiting the site. Provide protective clothing and/or equipment for the Employer and their representatives as appropriate.
A34/180 | WORK IN HAZARDOUS AREAS: Operatives must take the following precautions when working in the area(s) listed below:
| - | Work area: The southwest corner of the tower facing onto Newland Street where the building is elevated and in close proximity to the highway.
| - | Precautions: The scaffold is to have an integral crash deck to the underside and extending 1m either side to prevent any falling materials or tools from landing on members of the public or into the highway.
A34/185 | PERMIT to work procedures will operate for all hot work carried out inside the building and to the external roof.
HOT WORKS POLICY
A34/186 |  | FIRE PRECAUTIONS:
| - | Take all necessary precautions to prevent personal injury, death, and damage to the Works or other property from fire. No inflammable materials are to be stored within the building. Provide a nine litre water type extinguisher on site at all times, maintained at the recommended intervals. Supply all other equipment necessary as described in the Joint Fire Code, if applicable, including manual sounders, signage, fire stopping and fire marshals.
A34/187 | HEAT EMITTING LAMPS
| - | (Halogen) are not to be used in temporary site lighting.
A34/190 | EXISTING FIRE PRECAUTIONS:
| - | Obtain from the Employer or CA, before commencement, advice on existing fire detection and alarm systems in the property, call points, fire extinguisher positions, fire escape routes, nearest telephone and Fire Station and procedures to be followed in the case of a fire, and incorporate within the Principal Contractors Construction Phase Health and Safety Plan.
PROTECT AGAINST THE FOLLOWING:
A34/221 | NOISE:
| - | Comply generally with the recommendations of BS 5228: Part 1, clause 9.3 for minimising noise levels during the execution of the works.
| - | Noise levels from the works are to be kept as quiet as possible. Workers are to converse in low volumes unless a critical health and safety response demands otherwise.
| - | Fit all compressors, percussion tools and vehicles with effective silencers of a type recommended by manufacturers of the compressors, tools or vehicles.
| - | Avoid the use pneumatic drills and other noisy appliances wherever possible.
| - | Do not use or permit employees to use radios or other audio equipment.
A34/230 | POLLUTION: Take all reasonable precautions to prevent pollution of the site, the Works and the general environment including streams and waterways. If pollution occurs, inform the appropriate Authorities and the CA without delay and provide them with all relevant information.
A34/236 | USE OF PESTICIDES will not be permitted.
A34/240 | NUISANCE: Take all necessary precautions to prevent nuisance from smoke, dust, rubbish, vermin and other causes.
A34/250 | ASBESTOS BASED MATERIALS: Report immediately to the CA any suspected asbestos based materials discovered during demolition/refurbishment work. Avoid disturbing such materials. Agree with the CA methods for safe removal or encapsulation.
A34/260 | FIRE PREVENTION: Take all necessary precautions to prevent personal injury, death, and damage to the Works or other property from fire. Comply with Joint Code of Practice ‘Fire Prevention on Construction Sites’ published by the Building Employers Confederation and the Loss Prevention Council.
A34/263 | FIRE PREVENTION: Smoking is not be permitted anywhere on or near to the site.
A34/265 | BURNING ON SITE of materials arising from the work will not be permitted.
A34/270 | WATER: Prevent damage from storm and surface water. (Items for keeping the site and excavations free of water are given elsewhere).
A34/280 | MOISTURE: Prevent the work from becoming wet or damp where this may cause damage. Dry out the Works thoroughly. Control the drying out and humidity of the Works and the application of heat to prevent:
| - | Blistering and failure of adhesion.
| - | Damage due to trapped moisture.
| - | Excessive movement.
A34/285 | INFECTED TIMBER: Where instructed to remove timber affected by fungal/insect attack from the building, do so in a way which will minimise the risk of infecting other parts of the building.
A34/290 | WASTE:
| - | Remove rubbish, debris, surplus material and spoil daily and keep the site and keep the Works spotlessly clean and tidy (dust control forms a key part of the project).
| - | Remove all rubbish, dirt, cobwebs and residues by vacuuming from the existing building at the commencement of each bay.
| - | Ensure that non-hazardous material is disposed of legally at a recycling and waste facility approved by a Waste Regulation Authority.
| - | Remove all surplus hazardous materials and their containers regularly for disposal off site in a safe and competent manner as approved by a Waste Regulation Authority and in accordance with relevant regulations.
| - | Retain waste transfer documentation.
PROTECT THE FOLLOWING:
A34/410 | WORK IN ALL SECTIONS: Adequately protect all types of work and all parts of the Works, including work carried out by others, throughout the Contract. Wherever work is of an especially vulnerable nature or is exposed to abnormal risks provide special protection to ensure that damage does not occur.
A34/420 | EXISTING SERVICES:
| - | Before starting work check positions of existing mains/services. Where positions are not shown on drawings obtain relevant details from service authorities or other owners.
| - | Adequately protect, and prevent damage to all services. Do not interfere with their operation without consent of the service authorities or other owners.
| - | If any damage to services results from the execution of the Works, notify the CA and appropriate service authority without delay. Make arrangements for the work to be made good without delay to the satisfaction of the service authority or other owner as appropriate. Any measures taken by the CA to deal with an emergency will not affect the extent of the Contractor’s liability.
| - | Replace any marker tapes or protective covers disturbed during site operations to the service authority’s recommendations.
A34/490 | EXISTING STRUCTURES:
| - | Provide and maintain during the execution of the Works all incidental shoring, strutting, needling and other supports as may be necessary to preserve the stability of existing structures on the site or adjoining, that may be endangered or affected by the Works.
| - | Support existing structure as necessary during cutting of new openings or replacement of structure.
| - | Do not remove supports until new work is strong enough to support the existing structure. Prevent overstressing of completed work when removing supports.
A36 | FACILITIES/TEMPORARY WORK/SERVICES
GENERALLY
A36/110 | LOCATIONS: Inform the CA of the intended siting of all skips, temporary works and services.
A36/120 | MAINTAIN, alter, adapt and move temporary works and services as necessary. Remove when no longer required and make good.
A36/260 | SANITARY ACCOMMODATION: Temporary accommodation within the site compound will need to be made available to workers and visitors to the site, allowing for male and female toilet accommodation. Mess facilities if required, are to be provided by the contractor. There is hot water on site and refreshments can be purchased from local conveniences in the town centre nearby.
SERVICES AND FACILITIES
A36/410 | LIGHTING: Provide temporary lighting, for the works.
A36/420 | LIGHTING AND POWER: Electricity supply from the Employer's mains may be used for the Works as follows:
| - | Supply will be 230V.
| - | The Employer will not be held responsible for the effects of any failure or restriction in supply.
| - | Point of supply: Three-pin sockets in the tower.
| - | Anticipated capacity: 3kW.
A36/430 | WATER from the Employer's mains may be used for the Works (avoidable waste excepted) as follows:
| - | Tower entrance at ground floor level.
A36/441 | TELEPHONES: The responsible site manager shall be contactable by mobile phone with adequate reception. A site telephone is not required.
A36/453 | E-MAIL FACILITY: It is expected that the site manager will be contactable by email on a daily basis (at the end of each working day).
A54 | PROVISIONAL WORKS/ ITEMS
A54/100 | PROVISIONAL SUMS
| - | All provisional sums are identified in red in the activity schedule.
A54/590 | CONTINGENCIES
| - | Allow a contingency of £49,794 to be included within the contract sum and instructed as a contract variation. Any contingency sums remaining at the end of the contract are to be omitted from the final contract figure. |  |  |  | 49794
A55 | DAYWORKS
A55/100 | PRIME COST OF DAYWORKS: to be calculated in accordance with the 'DEFINITION OF PRIME COST OF DAYWORK CARRIED OUT UNDER A BUILDING CONTRACT, refer to the contract clause 3.7.6 published by the RICS and BEC applies, subject to any amendments stated below.
A55/101 | Hourly Base Rates' for labour are to be computed in accordance with Item 3.2 of the above 'Definitions' and are to be inclusive of all incidental costs, overheads and profit as defined in Section 6 of the above 'Definitions'. They will be subject to no further adjustment. In the case of Plumbing operatives, the National Working Rules of the Joint Industry Boards of Plumbing, Mechanical Engineering Services shall apply and 'Hourly Base Rates' shall include for contributions to the relevant pension scheme.
A55/103 | Materials and goods as defined in Section 4 of the 'Definition', except that cash discounts allowable under Item 4.1 shall not exceed 2.5%.
A55/104 | Plant as defined in Section 5 of the above 'Definition' calculated in accordance with the 'Schedule of basic Plant Charges for Use in Connection with Daywork under a Building Contract, refer to the contract clause 3.7.6 published by the RICS.
A55/105 | Incidental costs, overheads and profit as defined in Section 6 of the Definition. Note: Hourly base rates for labour will be deemed to include all items referred to in Section 6 of the Definition.
A100 |  |  |  |  | Total of all prelims items A10-A55 | 50544

## B - Temporary Works
SECTION B - TEMPORARY WORKS |  |  |  | labour hrs | materials £ | subcon £ | prov sums £ | labour hrs | materials £ | subcon £ | prov sums £
Generally |  |  |  | 31.38 | /hr for 1 man
Note: The Tenderer's attention is drawn to the need for all temporary shoring, scaffolding etc. to be constructed in such a way that enable any dismantling & repairs to be undertaken carefully & safely. The levels of lifts' & positions of standards etc. are thus to be carefully considered and a a scaffold design is provided for contractor's to price from.
Temporary Scaffolding
Generally
Note: A scaffolding and hoarding license will need to be applied for by the Main Contractor and allow sufficient time for approval before scaffolding and hoarding is erected. Scaffolding will need to be offloaded on Market Place where it will be erected and to be undertaken at off-peak times during normal working hours, Monday to Friday. Hoardings and scaffold are to be made secure at all times where there is a high risk to public health and safety. Ladders and hoists will need to be fully secure to prevent members of the public from ascending the temporary structure.
Public events are planned for 2026/ 2027 and include the following:-
Remembrance Events and Services Sunday 8th and Wednesday 11th November 2026.
Coleford Christmas Lights Switch-On, TBC
External Scaffolding | [7 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
The Contractor is to allow for the erection of all external scaffolding as indicated on the drawings to allow for all dismantling, repair and alteration works as described in the Works Sections and complete with all protections to comply with all health and safety requirements in the provision of guard rails, kick boards etc., and obtain appropriate completion Certificate. Identify and include for separate elements as appropriate the following:- | [7 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
i) general access, works and protection scaffolding including temporary drainage for the tower | 1 | Item | 0 | 18 |  | 31121 | -2120 | 18 | 0 | 31121 | -2120
[8 empty] | 0 | 0 | 0 | 0
ii) goods hoist | 1 | Item | 0 |  |  | 10080 |  | 0 | 0 | 10080 | 0
[8 empty] | 0 | 0 | 0 | 0
iii) ladder access | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Allow for maintaining the scaffolding for the period required, altering and adapting as necessary to facilitate all works and for ensuring that the scaffold is inspected weekly in accordance with the relevant regulations and that the inspection records are kept in a Register, which should be maintained on site. Identify and include for separate elements as appropriate following:- | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
i) general access, works and protection scaffolding | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
ii) goods hoists | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
iii) ladder access | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Allow for obtaining approval from the Architect over the completion of all works requiring access via the scaffolding prior to and including striking and removing last scaffolding on completion. Identify and include for separate elements as appropriate following:- | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
i) general access, works and protection scaffolding | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
ii) goods hoists | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
iii) ladder access | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Debris Netting | [7 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
The above design is to include for providing and cladding scaffold neatly and tightly in debris netting if so directed, netting to be uniform colour as agreed with the Architect. Nettings should be suitable for working with mortars, allowing for protection against rapid drying and ensuring that good airflows can easily be maintained. | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Allow for obtaining approval from the Architect over the completion of all works prior to and including removing all debris netting on completion. | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Scaffold Security | [7 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Provide and install solid boarding to all scaffold faces accessible to the public to a minimum height of 2.4 metres. Boarding to have no protrusions or recesses that can act as holds for climbing and to consist stout treated softwood carcassing/framing attached to the scaffold poles with appropriate limpets. Boarding to be fully painted in colour to be agreed with the Architect. | 1 | Item | 0 |  |  | 3225 |  | 0 | 0 | 3225 | 0
[8 empty] | 0 | 0 | 0 | 0
All gates and other access through the perimeter hoarding are to be similarly detailed to offer only a solid boarded unscalable face externally to the same height as the other boarding, painted finish as the boarding. | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Allow for maintaining security hoarding & gates for the period required, altering and adapting as necessary to facilitate all works and to remedy any damage s soon as possible following discovery. |  | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
Allow for obtaining approval from the Architect over the completion of all works prior to and including striking and removing the boarding and gates and all supporting structure on completion. | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Further security may be required for the full contract duration. Allow for a scaffold alarm and CCTV to a private security company. | 1 | Item | 0 |  |  |  | 5000 | 0 | 0 | 0 | 5000
[8 empty] | 0 | 0 | 0 | 0
Internal Scaffolding
Allow for installing internal scaffoldings to the tower to provide full access as needed on all floors. Ensure that reasonable propping and shoring is in place prior to the internal scaffolds being erected.
i) general access, works and protection scaffolding | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
ii) ladder access | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
Allow for maintaining the scaffolding for the period required, altering and adapting as necessary to facilitate all works and for ensuring that the scaffold is inspected weekly in accordance with the relevant regulations and that the inspection records are kept in a Register, which should be maintained on site. Identify and include for separate elements as appropriate following:-
i) general access, works and protection scaffolding | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
ii) ladder access | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Temporary Shoring | [7 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Provide and maintain during the execution of the works all shoring, strutting, needling and other supports all as described in the Preliminaries and Specifications as may be necessary to preserve the stability of the remaining elements of the building that may be endangered or affected as the works are undertaken and at completion clear all away and make good all work disturbed. Identify and include for separate elements as appropriate following:- | [7 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
i) | 1 | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
Temporary Rainwater Disposal and Protection
Note: Details of dispersal arrangements are provided in the following sections and a further provisional sum is provided, and to be agreed with the Architect.
Allow the following PROVISIONAL SUM for temporary rainwater disposal and protection during the Works. |  |  | 300
Dust Protections
Unless otherwise defined or excluded from within the Main Contractor's preliminaries, additional dust protections are to be itemised below:-
i) |  | Item | 0
Allow the following PROVISIONAL SUM for additional dust protections not specified during the works. |  | Item | 500
Protection of Working Clock Mechanisms
Allow for working with the clock specialist for temporarily disconnecting and isolating all electrical clock mechanism parts that need to be removed in connection with the dismantling works. Allow for the full protection of all electrical clock working components for the full contract duration. The clock specialist will be appointed separately by the Employer and will be working directly for them. Access to the scaffolding will be required to remove the clock dials and reinstall them following off-site repair. The clock specialists have indicated that the work will take 10 weeks in total. |  | Item | 0
Asbestos Removal
Allow the following PROVISIONAL SUM for further asbestos testing and removal during the Works. |  | Item | 1000
Site Clearing at Completion
Allow for clearing the site at completion and making good of the site and surrounding landscaping to be at the Main Contractor's expense. Ensure that adequate protections are in place for the duration of the contract. |  | Item | 0
To Main Summary £ |  |  | 1800 |  |  |  |  | 18 | 0 | 44426 | 2880
[8 empty] | 564.84 | 0 | 48868.6 | 2880
52313.44
[10 empty] | Diff= | 50513.44

## C.1 - External Repairs
SECTION C.1 - EXTERNAL REPAIRS |  |  |  | labour hrs | materials £ | subcon £ | prov sums £ | labour hrs | materials £ | subcon £ | prov sums £
Notes |  |  |  | 31.38 | /hr for 1 man
This section of repairs involves the repairs to the external elevations. | 1 | Item | 0
All works to be undertaken as detailed on the drawings and to the Architect's Specification (shortened to AS in descriptions below). | 1 | Item | 0
Repairs to the clock dials in the north, west and south elevations to be undertaken by a specialist and works to be undertaken concurrently whilst scaffold access is in place. |  | Item | 0
Generally
Liaise with the Architect and allow for their attendance whilst inspecting and confirming works to the elevations. | 1 | Item | 0
In all removals, unless otherwise described, removal is to include all fixings and removal to an approved disposal point away from the site. | 1 | Item | 0
In all removals, and in particular leadwork, allow full CREDIT value as appropriate. | 1 | Item | 0
The Contractor is to be aware that in working within an existing building the previous use of hazardous materials may be encountered, such as asbestos. The Contractor is to maintain awareness of such possibility and fully acquaint themselves with the health and safety information and ensure all appropriate precautions are taken in undertaking the proposed repairs. | 1 | Item | 0
South Elevation
Masonry Repairs
Allow PROVISIONAL SUM for any additional repairs as they arise on site. |  | Item | 500
Undertake mortar repair/ conservation and re-pointing as NBS C41:
Rake out and re-point the door threshold step. | 1.7 | lm | 0
Conservation and mortar repairs to isolated areas no larger than 300 x 500mm. | 2 | Nr | 0
De-frass, rake-out and re-point joints in various locations as indicated. | 32 | m² | 0
Carry out the following stonework repairs as NBS F21:
Indent repair 200 x 150mm to plinth (including chopping-out and propping. Bed length TBC). | 1 | Nr | 0
Hood mould indent repair 130(d) x 130(w) x 500(l)mm (Including chopping-out and propping. Bed length TBC). | 1 | Nr | 0 |  |  |  |  | 0 | 0 | 0 | 0
Hood mould indent repair 130(d) x 150 x 700(l)mm (Including chopping-out and propping. Bed length TBC). | 1 | Nr | 0
Buttress coping indent repair 450(w) x 250(d) x 225h(h)mm (Including chopping-out and propping. Bed length TBC). | 3 | Nr | 0
Sloping string course indent repair 600(w) x 110(d) x 100(h)mm (Including chopping-out and propping. Bed length TBC). | 1 | Nr | 0
Sloping string course indent repair 400(w) x 110(d) x 100(h)mm (Including chopping-out and propping. Bed length TBC). | 1 | Nr | 0
Render Repairs
Removals
Undertake trial removal area at the base of the buttress to be one course high by full width of the buttress to determine the condition of the stonework behind and expediency of the work. Remove existing render using hand tools only. | 0.3 | m² | 0
Remove remaining rendered areas using hand tools only. | 4.4 | m² | 0
New Render Application
Install new lined-out three coat lime:sand render system to the south-east buttress. | 4.7 | m² | 0
Timber Repairs
Allow PROVISIONAL SUM for repairs to the Belfry louvered lancet window as they arise on site. |  | Item | 300
Allow for light cleaning of timber louvres removing bird guano |  | Item | 0
Replace the chamfered rotten oak cill to the main entrance door (25(d) x 85(h) x 560(w)mm using well seasoned oak to match. |  | Item | 0
Oak splice repair to the lower door plank (20(d) x 90(w) x 200(h)mm) in the main entrance doors using well seasoned oak. Existing studs to be carefully removed and reinstated upon completion. |  | Item | 0
Leaded Light Window Repairs and Reinstatement
GRP panels to be carefully removed to WFF.01 as section C.4 - Internal Alterations and Repairs.
Allow PROVISIONAL SUM for stone repairs to the window embrasures following removal of the GRP panels and as they arise on site. |  | Item | 100
Carefully cut off vertical ferramenta feet and fit new grade 316 stainless steel tips with joggle joints (methodology to be confirmed with the glazing sub-contractor) | 4 | Nr | 0
Carefully remove existing paint from all ferramenta with a wire brush and redecorate in satin black paint as M60. | 4 | Nr | 0
Reinstate ferramenta prior to new leaded glass lights being installed. | 4 | Nr | 0
Install a code 6 lead tray to the window cill leaving a 10mm air gap below the leaded light panel for ventilation. Fix the tray internally over a HW bearer and lead detail to be finished in a welt. Lead tray to be extended up the face of the external window jambs and chased into position along the lines of the lowest bed joint not less than 100mm above the base of the leaded light. |  | Item | 0
Install the new leaded diamond light as the Architect's drawings and AS. |  | Item | 0
Re-point leaded light panel in lime mortar. | 3.4 | lm | 0
Miscellaneous
De-rust and apply a rust inhibitor to the projecting metal bars bedded in the wall either side of the entrance door. | 2 | Nr | 0
West Elevation
Masonry Repairs
Allow PROVISIONAL SUM for any additional repairs as they arise on site. |  | Item | 500
Undertake mortar repair/ conservation and re-pointing as NBS C41:
Conservation and mortar repairs to isolated areas no larger than 100 x 150mm. | 3 | Nr | 0
Conservation and mortar repairs to isolated areas no larger than 250 x 300mm. | 1 | Nr | 0
De-frass, rake-out and re-point joints in various locations as indicated. | 28 | m² | 0
Carry out the following stonework repairs as NBS F21:
Hood mould indent repair 130(d) x 130(w) x 200(l)mm (Including chopping-out and propping. Bed length TBC). | 1 | Nr | 0 |  |  |  |  | 0 | 0 | 0 | 0
Buttress coping indent repair 450(w) x 250(d) x 225h(h)mm (Including chopping-out and propping. Bed length TBC). | 5 | Nr | 0
Buttress stone indent repair 230(h) x 170(w)mm (Including chopping-out and propping. Bed length TBC). | 1 | Nr | 0
Sloping string course indent repair 450(w) x 110(d) x 100(h)mm (Including chopping-out and propping. Bed length TBC). | 1 | Nr | 0
Render Repairs
Removals
Remove the existing render to the infilled opening. Render applied to modern concrete blockwork background. | 3.3 | m² | 0
New Render Application
Install new lined-out three coat lime:sand render system to the blank arch opening. | 3.3 | m² | 0
Timber Repairs
Allow PROVISIONAL SUM for repairs to the Belfry louvered lancet window as they arise on site. |  | Item | 300
Allow for light cleaning of timber louvres removing bird guano |  | Item | 0
Leaded Light Window Repairs and Reinstatement
GRP panels to be carefully removed to WFF.02 as section C.4 - Internal Alterations and Repairs.
Allow PROVISIONAL SUM for stone repairs to the window embrasures following removal of the GRP panels and as they arise on site. |  | Item | 100
Carefully cut off vertical ferramenta feet and fit new grade 316 stainless steel tips with joggle joints (methodology to be confirmed with the glazing sub-contractor) | 4 | Nr | 0
Carefully remove existing paint from all ferramenta with a wire brush and redecorate in satin black paint as M60. | 4 | Nr | 0
Reinstate ferramenta prior to new leaded glass lights being installed. | 4 | Nr | 0
Install a code 6 lead tray to the window cill leaving a 10mm air gap below the leaded light panel for ventilation. Fix the tray internally over a HW bearer and lead detail to be finished in a welt. Lead tray to be extended up the face of the external window jambs and chased into position along the lines of the lowest bed joint not less than 100mm above the base of the leaded light. |  | Item | 0
Install the new leaded diamond light as the Architect's drawings and AS. |  | Item | 0
Re-point leaded light panel in lime mortar. | 3.4 | lm | 0
North Elevation
Masonry Cleaning
Undertake stone cleaning as NBS C40:
Lower sloping string course. | 1.4 | m² | 0
Mid sloping string course. | 0.9 | m² | 0
Upper sloping string course. | 1.3 | m² | 0
Below belfry lancet louvered window and clock dial (ensure that clock dial is removed before carrying out cleaning works). | 2.8 | m² | 0
Masonry Repairs
Allow PROVISIONAL SUM for any additional repairs as they arise on site. |  | Item | 500
Undertake mortar repair/ conservation and re-pointing as NBS C41:
Rake out and re-point the door threshold step. | 1.7 | lm | 0
Conservation and mortar repairs to isolated areas no larger than 300 x 500mm. | 2 | Nr | 0
De-frass, rake-out and re-point joints in various locations as indicated. | 32 | m² | 0
Carry out the following stonework repairs as NBS F21:
Indent repair 200 x 150mm to plinth (including chopping-out and propping. Bed length TBC). | 1 | Nr | 0
Hood mould indent repair 130(d) x 130(w) x 500(l)mm (Including chopping-out and propping. Bed length TBC). | 1 | Nr | 0 |  |  |  |  | 0 | 0 | 0 | 0
Hood mould indent repair 130(d) x 150 x 700(l)mm (Including chopping-out and propping. Bed length TBC). | 1 | Nr | 0
Buttress coping indent repair 450(w) x 250(d) x 225h(h)mm (Including chopping-out and propping. Bed length TBC). | 3 | Nr | 0
Sloping string course indent repair 600(w) x 110(d) x 100(h)mm (Including chopping-out and propping. Bed length TBC). | 1 | Nr | 0
Sloping string course indent repair 400(w) x 110(d) x 100(h)mm (Including chopping-out and propping. Bed length TBC). | 1 | Nr | 0
Render Repairs
Removals
Undertake trial removal area at the base of the buttress to be one course high by full width of the buttress to determine the condition of the stonework behind and expediency of the work. Remove existing render using hand tools only. | 0.3 | m² | 0
Remove remaining rendered areas using hand tools only. | 4.4 | m² | 0
New Render Application
Install new lined-out three coat lime:sand render system to the south-east buttress. | 4.7 | m² | 0
Timber Repairs
Allow PROVISIONAL SUM for repairs to the Belfry louvered lancet window as they arise on site. |  | Item | 300
Replace the chamfered rotten oak cill to the main entrance door (25(d) x 85(h) x 560(w)mm using well seasoned oak to match. |  | Item | 0
Oak splice repair to the lower door plank (20(d) x 90(w) x 200(h)mm) in the main entrance doors using well seasoned oak. Existing studs to be carefully removed and reinstated upon completion. |  | Item | 0
Leaded Light Window Repairs and Reinstatement
GRP panels to be carefully removed to WFF.01 as section C.4 - Internal Alterations and Repairs.
Allow PROVISIONAL SUM for stone repairs to the window embrasures following removal of the GRP panels and as they arise on site. |  | Item | 100
Carefully cut off vertical ferramenta feet and fit new grade 316 stainless steel tips with joggle joints (methodology to be confirmed with the glazing sub-contractor) | 4 | Nr | 0
Carefully remove existing paint from all ferramenta with a wire brush and redecorate in satin black paint as M60. | 4 | Nr | 0
Reinstate ferramenta prior to new leaded glass lights being installed. | 4 | Nr | 0
Install a code 6 lead tray to the window cill leaving a 10mm air gap below the leaded light panel for ventilation. Fix the tray internally over a HW bearer and lead detail to be finished in a welt. Lead tray to be extended up the face of the external window jambs and chased into position along the lines of the lowest bed joint not less than 100mm above the base of the leaded light. |  | Item | 0
Install the new leaded diamond light as the Architect's drawings and AS. |  | Item | 0
Re-point leaded light panel in lime mortar. | 3.4 | lm | 0
Miscellaneous
De-rust and apply a rust inhibitor to the projecting metal bars bedded in the wall either side of the entrance door. | 2 | Nr | 0
East Elevation
Masonry Repairs
Allow PROVISIONAL SUM for any additional repairs as they arise on site. |  | Item | 500
Undertake mortar repair/ conservation and re-pointing as NBS C41:
Rake out and re-point the door threshold step. | 1.7 | lm | 0
Conservation and mortar repairs to isolated areas no larger than 300 x 500mm. | 2 | Nr | 0
De-frass, rake-out and re-point joints in various locations as indicated. | 32 | m² | 0
Carry out the following stonework repairs as NBS F21:
Indent repair 200 x 150mm to plinth (including chopping-out and propping. Bed length TBC). | 1 | Nr | 0
Hood mould indent repair 130(d) x 130(w) x 500(l)mm (Including chopping-out and propping. Bed length TBC). | 1 | Nr | 0 |  |  |  |  | 0 | 0 | 0 | 0
Hood mould indent repair 130(d) x 150 x 700(l)mm (Including chopping-out and propping. Bed length TBC). | 1 | Nr | 0
Buttress coping indent repair 450(w) x 250(d) x 225h(h)mm (Including chopping-out and propping. Bed length TBC). | 3 | Nr | 0
Sloping string course indent repair 600(w) x 110(d) x 100(h)mm (Including chopping-out and propping. Bed length TBC). | 1 | Nr | 0
Sloping string course indent repair 400(w) x 110(d) x 100(h)mm (Including chopping-out and propping. Bed length TBC). | 1 | Nr | 0
Render Repairs
Removals
Undertake trial removal area at the base of the buttress to be one course high by full width of the buttress to determine the condition of the stonework behind and expediency of the work. Remove existing render using hand tools only. | 0.3 | m² | 0
Remove remaining rendered areas using hand tools only. | 4.4 | m² | 0
New Render Application
Install new lined-out three coat lime:sand render system to the south-east buttress. | 4.7 | m² | 0
Timber Repairs
Allow PROVISIONAL SUM for repairs to the Belfry louvered lancet window as they arise on site. |  | Item | 300
Replace the chamfered rotten oak cill to the main entrance door (25(d) x 85(h) x 560(w)mm using well seasoned oak to match. |  | Item | 0
Oak splice repair to the lower door plank (20(d) x 90(w) x 200(h)mm) in the main entrance doors using well seasoned oak. Existing studs to be carefully removed and reinstated upon completion. |  | Item | 0
Leaded Light Window Repairs and Reinstatement
GRP panels to be carefully removed to WFF.01 as section C.4 - Internal Alterations and Repairs.
Allow PROVISIONAL SUM for stone repairs to the window embrasures following removal of the GRP panels and as they arise on site. |  | Item | 100
Carefully cut off vertical ferramenta feet and fit new grade 316 stainless steel tips with joggle joints (methodology to be confirmed with the glazing sub-contractor) | 4 | Nr | 0
Carefully remove existing paint from all ferramenta with a wire brush and redecorate in satin black paint as M60. | 4 | Nr | 0
Reinstate ferramenta prior to new leaded glass lights being installed. | 4 | Nr | 0
Install a code 6 lead tray to the window cill leaving a 10mm air gap below the leaded light panel for ventilation. Fix the tray internally over a HW bearer and lead detail to be finished in a welt. Lead tray to be extended up the face of the external window jambs and chased into position along the lines of the lowest bed joint not less than 100mm above the base of the leaded light. |  | Item | 0
Install the new leaded diamond light as the Architect's drawings and AS. |  | Item | 0
Re-point leaded light panel in lime mortar. | 3.4 | lm | 0
Miscellaneous
De-rust and apply a rust inhibitor to the projecting metal bars bedded in the wall either side of the entrance door. | 2 | Nr | 0
To Main Summary £ |  |  | 3600

## C.2 - Roof Repairs
SECTION C.2 - ROOF REPAIRS |  |  |  | labour hrs | materials £ | subcon £ | prov sums £ | labour hrs | materials £ | subcon £ | prov sums £
Notes |  |  |  | 31.38 | /hr for 1 man
This section of repairs involves the roof, with associated renewal of stepped lead gutters and external drainage. | 1 | Item | 0
All works to be undertaken as detailed on the drawings and to the Architect's Specification (shortened to AS in descriptions below). All new leadwork to also be installed as the Lead Sheet Association's Rolled lead Sheet - The Complete Manual and as the latest guidance of BS EN 12588. | 1 | Item | 0
Generally
Liaise with the Architect and allow for their attendance whilst inspecting and confirming works to the roofs. | 1 | Item | 0
In all removals, unless otherwise described, removal is to include all fixings and removal to an approved disposal point away from the site. | 1 | Item | 0
In all removals, and in particular leadwork, allow full CREDIT value as appropriate. | 1 | Item | 0
Allow for the removal of all existing roof slates and to be replaced with new quantities. Existing slates to be carefully removed and set aside for inspection by the Architect. Existing slates are to be either re-used or sold for reclamation. |  | Item | 0
The Contractor is to be aware that in working within an existing building the previous use of hazardous materials may be encountered, such as asbestos. The Contractor is to maintain awareness of such possibility and fully acquaint themselves with the health and safety information and ensure all appropriate precautions are taken in undertaking the proposed repairs. | 1 | Item | 0
Roof
Removals
Carefully allow for the removal/ adjustments to the existing gantries and walkways on both sides of the roof, and central Christmas lights display base as required to access the work areas and set aside for re-use and re-fixing. Allow for reinstatement upon completion. |  | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
Carefully remove the existing ridge slates and set aside for inspection by the Architect for re-use. |  | Item | 0
[8 empty] | 0 | 0 | 0 | 0
Carefully strip the north roof slope and set aside existing slates for inspection by the Architect for re-use. Slates to be stored on the scaffolding. Allow for the full removal of existing battens and modern roofing felt and cart away. |  | m | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Carefully strip the south roof slope and set aside existing slates for inspection by the Architect for re-use. Slates to be stored on the scaffolding. Allow for the full removal of existing battens and modern roofing felt and cart away. |  | m | 0 | 18 |  | 31121 | -2120 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Rake out the mortar joints to the lead gutter abutment flashings in the north parapet elevation. |  | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Rake out the mortar joints to the lead gutter abutment flashings in the west parapet elevation. |  | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Rake out the mortar joints to the lead gutter abutment flashings in the south parapet elevation. |  | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Rake out the mortar joints to the lead gutter abutment flashings in the east parapet elevation. |  | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Roof Carpentry Repairs | [7 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Allow the following PROVISIONAL SUM for repairs to existing roof structures once exposed and extent of repairs to be confirmed by the Architect and executed by a qualified carpenter. | 1 | Item | 1000 |  |  |  |  | 0 | 0 | 0 | 0
Allow the following PROVISIONAL SUM for repairs to existing roof hatch following removal of the lead coverings. Once exposed extent of repairs to be confirmed by the Architect and executed by a qualified carpenter as required. Allow for installing new ironmongery on the internal side. |  | Item | 450
[8 empty] | 0 | 0 | 0 | 0
Roof Recovering | [7 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Supply and fit new breathable roof membrane as the specification with 50 x 25mm treated softwood timber battens in the north roof. | 17.4 | m | 0 |  |  |  |  | 0 | 0 | 0 | 0
Supply and fit new breathable roof membrane as the specification with 50 x 25mm treated softwood timber battens in the south roof. | 17.4 | m | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Supply and fit a new treated softwood timber tilting fillet at the eaves to the valley gutter in the north roof set out to suit new slating as the Architect's drawings and AS. | 5 | m | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Supply and fit new eaves fascia vent and proprietary underlay support to the north roof to improve ventilation as the Architect's drawings and AS. | 5 | m | 0 |  |  |  |  | 0 | 0 | 0 | 0
Supply and fit a new treated softwood timber tilting fillet at the eaves to the valley gutter in the south roof set out to suit new slating as the Architect's drawings and AS. | 5 | m | 0
[8 empty] | 0 | 0 | 0 | 0
Supply and fit new eaves fascia vent and proprietary underlay support to the south roof to improve ventilation as the Architect's drawings and AS. | 5 | m | 0 |  |  |  |  | 0 | 0 | 0 | 0
Supply and fit new ridge vent and proprietary underlay support to the south roof to improve ventilation as the Architect's drawings and AS. | 5 | m | 0
Supply and fit new ridge vent and proprietary underlay support to the north roof to improve ventilation as the Architect's drawings and AS. | 5 | m | 0
Re-slate the north roof slope in new slates as the Architect's drawings and AS. | 12 | m² | 0
Re-slate the south roof slope in new slate as the Architect's drawings and AS. | 12 | m² | 0
[8 empty] | 0 | 0 | 0 | 0
Lead Parapet Abutment Flashing Repairs
Note: The dimensions for flashing lengths and secret gutters given below are for guide purposes. Actual dimensions are to be ascertained on site and pricing is to reflect actual dimensions.
Note: Secret gutters are to be installed in the east and west parapet roof to wall abutments, replacing the existing lead soakers. The width of each secret gutter piece will be 65mm minimum height from above the slate or tile roof finishes with a 25mm wide gutter extending over a new treated softwood 25 x 50mm verge batten to provide a single-welt finish for the internal free edge of the leadwork. Gutter lining pieces should not exceed 1.5m lengths and to be fixed securely at the head only with a minimum 100mm head lap. Cover flashings are to be continuous in the west parapet and not exceed 1.5m lengths.
Note: Perimeter cover flashings are to provide minimum 100mm cover against all lead upstands and cover flashings to be in code 6 lead.
Flashings - Removals
Carefully withdraw the existing flashings and secret lead gutters from the east and west parapet stonework in the north Nave roof and remove from site allowing CREDIT as appropriate. | 21.6 | m | 0
Thoroughly clean out the grooves to the north, south, east and west parapets and remove all arisings from site, making good and preparing the grooves as the AS to receive the new lead flashings. | 21.6 | m | 0
[8 empty] | #REF! | #REF! | #REF! | #REF!
Abutment Flashings - New Work
Supply and fix new Code 6 lead cover flashing into the grooves in the prepared stonework to the north parapet, including for lead wedging/screw fixing and mortar pointing, to the Architects specification. | 5 | m | 0
Extra over for returns at the end of the gutters and to be single-welted to the internal free edge side. Actual dimensions to be ascertained on site. | 1.7 | m | 0
Supply and fix new Code 6 lead cover flashing into the grooves in the prepared stonework to the south parapet, including for lead wedging/screw fixing and mortar pointing, to the Architects specification. | 5 | m | 0
Extra over for returns at the end of the gutters and to be single-welted to the internal free edge side. Actual dimensions to be ascertained on site. | 1.7 | m | 0
#REF!
Supply and fix new Code 6 secret gutters and cover flashings to the sloping roof abutment in the west parapet. Cover flashing to be chased and wedged into existing grooves/ joints and new leadwork to AS. | 4 | m | 0
[10 empty] | Diff= | #REF!
Extra over for increased splay at the base of the gutter and to be single-welted to the internal free edge side. Actual dimensions to be ascertained on site. | 2 | Nr | 0
Supply and fix new Code 6 secret gutters and cover flashings to the sloping roof abutment in the east parapet. Cover flashing to be chased and wedged into existing grooves/ joints and new leadwork to AS. | 4 | m | 0
Extra over for increased splay at the base of the gutter and to be single-welted to the internal free edge side. Actual dimensions to be ascertained on site. | 2 | Nr | 0
Stepped Lead Gutter Repairs
Note: The dimensions for gutter lining girths and bases given below are for guide purposes. Actual dimensions are to be ascertained on site and pricing is to reflect actual dimensions.
Note: Gutter linings to extend 150mm minimum up the slope of the roof to the base of the tilting fillet at the highest point of the gutter, with gutter linings to be extended over the fillet terminating in a single-welt detail. The width of the gutter increases with each drip and lead rolls are to be used should the maximum girth be exceeded, although this is not anticipated. Drips between each gutter length to be a minimum of 60mm for Code 7 lead.
Note: Historic outlets to be reinstated in the east elevation and gutter levels to be determined by the existing outlet levels on site.
Note: Refer to plans and gutter sections for details on individual outlets in the east elevation and Code 7 lead to be used for chutes.
Generally
Carefully disconnect the existing downpipe outlets in the north and south gutters and provide temporarily rainwater dispersal arrangements | 2 | Nr | 0
Carefully disconnect from downpipes, etc., and take up and remove all leadwork from gutter linings to the north gutter to include sides in running length, etc., gutter to varying depths. Remove arisings from site allowing CREDIT for lead. | 5 | m | 0
Carefully disconnect from downpipes, etc., and take up and remove all leadwork from gutter linings to the south gutter to include sides in running length, etc., gutter to varying depths. Remove arisings from site allowing CREDIT for lead. | 5 | m | 0
Carefully withdraw existing lead covering on top of the hatch and sides, apron, back gutter, soakers and flashings. Remove arisings from site allowing CREDIT for lead. |  | Item | 0
Thoroughly clean out grooves and remove all arisings from site, making good and preparing the grooves as AS to receive new lead flashings. | 7.8 | m | 0
Carefully remove lead soakers from the roof gable abutment in the west and east parapet elevations. Remove arisings from site allowing CREDIT for lead. | 8 | m | 0
Allow for carefully removing all existing boarding, firrings, bearers and all edge supports, etc., of the box and valley gutter linings, with an average of 300mm wide, to varying depths. Denail and defrass exposed structure and remove all arisings from site. | 10 | m | 0
Repairs and New Work
Allow for supplying and fixing new gutter boarding, re-laid to 1 in 50 falls and runs, to provide a minimum 300mm wide gutter base, 2500mm maximum length between drips and drips to be a minimum height of 60mm between gutter lengths. Boards to be penny gap ex 150x32mm treated softwood timber on and including new treated sawn timber gutters bearers and battens as appropriate to match the existing details where exposed internally, and in accordance with the Architect after inspection. | 10 | m | 0
Supply and fix new Code 7 lead gutter linings to the new boarding in the south and north gutters and laid to 1 in 50 falls as specified, in varying depths and some 1000mm wide girth (exact dimensions to be determined on site), including dressing and fixing around the drips, rolls and into sumps and turning up one side against masonry in varying heights, turning up the other side and dressing to below flashing of roof slating, also in varying heights. All to the Architects detailed drawings and the AS. | 10 | m | 0
Extra over for providing gutter chute in Code 7 lead in the east parapet wall, exact sizes and depths to suit the site condition, neatly fitting and dressed to the downpipe hopper. | 2 | Nr | 0
Ensure drain pipes are free flowing and discharge correctly into the external hopper following completions of the work | 2 | Nr | 0
Ensure drain pipes are free flowing and discharge correctly into the external hopper. | 1 | Nr | 0
Roof Access Hatch
Allow the following PROVISIONAL SUM for removing and replacing the existing access hatch with a new Bilco S-50TB roof hatch. To include retaining existing structures and trimming to suit the new hatch, proprietary flashings and fixings for ladders. |  | Item | 1200
Masonry Repairs
Allow the following PROVISIONAL SUM for locally de-frassing and applying a shelter coat to the internal parapet stonework. |  | Item | 1000
Allow the following PROVISIONAL SUM for lime mortar pointing repairs as the AS to the internal parapet areas. |  | Item | 1500
De-frass and apply a shelter coat to the pinnacles' masonry as the AS. | 4 | m² | 0
Rake out and repoint the pinnacles in the external tower corners using lime mortar and as the AS. | 4 | m² | 0
Decorations
Clean and redecorate the lower wall section weather vane components in the south parapet elevation as the AS. |  | Item | 0
Clean and redecorate the flag mast pole in the north parapet elevation as the AS. |  | Item | 0
Miscellaneous
Install the bat box in north parapet as the AS and Architect's drawings. |  | Item | 0
Install the bird box in the south parapet as the AS and the Architect's drawings. |  | Item | 0
To Main Summary £ |  |  | 5150

## C.3 - External Alterations
SECTION C.3 - EXTERNAL ALTERATIONS |  |  |  | labour hrs | materials £ | subcon £ | prov sums £ | labour hrs | materials £ | subcon £ | prov sums £
Notes |  |  |  | 31.38 | /hr for 1 man
This section involves alterations to the external elevations including the installation of 2nr. Fixed steel framed windows. | 1 | Item | 0
All works to be undertaken as detailed on the drawings and to the Architect's Specification (shortened to AS in descriptions below). | 1 | Item | 0
This section involves the CDP item for installing new steel framed fixed windows to the reinstated openings in the east elevation.
Generally
Liaise with the Architect and allow for their attendance whilst inspecting and confirming works to the roofs. | 1 | Item | 0
In all removals, unless otherwise described, removal is to include all fixings and removal to an approved disposal point away from the site. | 1 | Item | 0
The Contractor is to be aware that in working within an existing building the previous use of hazardous materials may be encountered, such as asbestos. The Contractor is to maintain awareness of such possibility and fully acquaint themselves with the health and safety information and ensure all appropriate precautions are taken in undertaking the proposed repairs. | 1 | Item | 0
East Elevation
Removals
Carefully allow for the removal/ adjustments to the 2nr. existing infilled openings at the top of the internal ground floor stairs following the removal of the existing cementitious render. Allow for the removal of all existing brick by hand and set aside bricks for client reuse. |  | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Making Good Existing Openings | [7 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Allow the following PROVISIONAL SUM for making good and repairing the masonry openings following the removal of the existing brickwork. |  | Item | 1000 |  |  |  |  | 0 | 0 | 0 | 0
Design and Installation of New Steel Framed Windows
Refer to drawings 1398 (40)01 and 1398 (50)01 showing the opening dimensions and detail intent drawing. Refer to specification L20 for details and finishes. |  | Item | 0
i) The outline design defined in this section and on the drawings is indicative. The appointed Contractor is responsible for developing the detailed design in accordance with these documents. |  | Item | 0
ii) Installation: The window installer shall be a specialist designer and the Main Contractor is to submit details. |  | Item | 0
iv) Warranty and Guarantee: The designer shall supply a copy of the warranty/ guarantee to the Employer within 14 days of completion. |  | Item | 0
#REF!
Allow the PROVISIONAL SUM for installing Code 6 lead weatherings to the base of the windows as necessary to ensure good water run-off where required. Detail requirements to be reviewed with the Main Contractor on site. Lead flashing to be dressed over the new lime render finishes |  | Item | 800
[10 empty] | Diff= | #REF!
To Main Summary £ |  |  | 1800

## C.4 - Internal Repairs
SECTION C.4 - INTERNAL ALTERATIONS AND REPAIRS |  |  |  | labour hrs | materials £ | subcon £ | prov sums £ | labour hrs | materials £ | subcon £ | prov sums £
Notes |  |  |  | 31.38 | /hr for 1 man
This section involves the internal areas, including strip out, making good and repairs on all floors. | 1 | Item | 0
All works to be undertaken as detailed on the drawings and to the Architect's Specification (shortened to AS in descriptions below). | 1 | Item | 0
It is assumed that all internal areas will be cleared of stored items by the Employer prior to the works commencing to ensure that all the spaces are fully accessible for use by the Main Contractor.
Generally
Liaise with the Architect and allow for their attendance whilst inspecting and confirming works to the internal areas. | 1 | Item | 0
In all removals, unless otherwise described, removal is to include all fixings and removal to an approved disposal point away from the site. | 1 | Item | 0
The Contractor is to be aware that in working within an existing building the previous use of hazardous materials may be encountered, such as asbestos. The Contractor is to maintain awareness of such possibility and fully acquaint themselves with the health and safety information and ensure all appropriate precautions are taken in undertaking the proposed repairs. | 1 | Item | 0
For general protection and access see Section B - Temporary Works. Other requirements to be noted here include temporary stair edge protections whilst repairs are being carried out to the historic metal balustrades, exposed and unprotected edges to the first floor mezzanine and temporary protections to the window openings following the removal of the existing GRP screens as required. |  | Item | 0
Allow for protecting all internal fixtures and fittings being retained for the full duration of the Works. |  | Item | 0
Strip Out and Removals
Ground Floor
Carefully remove the modern steel stair enclosure to the base of the internal south stair. |  | Item | 0
Carefully remove the existing downpipe and provide temporary rainwater protections as section C.2 - Roof Repairs. |  | Item | 0
Carefully allow for the removal of the services cupboard in the south external wall. |  | Item | 0 |  |  |  |  | 0 | 0 | 0 | 0
Remove the modern fluorescent lighting strip and redundant conduit in the south external elevation and as section C.6 - Electrical Services. |  | Item | 0
Carefully remove 2no. redundant metal brackets in the west internal elevation. | 2 | Nr | 0
Carefully remove the modern timber pattress to the internal side of the main entrance doors. |  | Item | 0
Carefully remove the modern masonry infill to the historic nave opening in the east elevation and provide temporary propping as required. |  | Item | 0
Carefully remove the modern paint finishes as the AS and the Architect's drawings to the modern blockwork infilled door openings in the west and north elevations. Ensure that all adjoining areas are fully protected whilst paint removal is carried out. | 6.6 | m² | 0
Carefully remove the modern paint finishes as the AS and the Architect's drawings to the modern blockwork infilled door openings in the west and north elevations. Ensure that all adjoining areas are fully protected whilst paint removal is carried out. | 1 | m² | 0
[8 empty] | 0 | 0 | 0 | 0
Internal Stair and Vestibules
Carefully allow for the removal of the modern masonry infill to the historic nave gallery openings accessed from the top of the internal stairs in the east elevation and provide temporary propping as required. | 2 | Nr | 0
First Floor and Clock Gantry
Carefully remove the modern GRP panels to the window openings in the north, west and south elevations. | 3 | Nr | 0 |  |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Carefully remove the existing downpipe and provide temporary rainwater protections as section C.2 - Roof Repairs. |  | Item | 0
Remove the modern timber batten and redundant wiring in the south external elevation. |  | Item | 0
Remove the modern gate to the top of the internal stairs in the east external elevation. |  | Item | 0
Carefully remove the modern OSB flooring throughout, but firstly undertake a trial area to determine the condition and quantity of any floorboards below. Provide temporary walkways and propping to the underside of the ceiling to facilitate the site investigations and need for additional supports. | 16.7 | m² | 0
Remove the existing edge protections to the opening in the floor and temporarily protect the edges as required. | 1.5 | m | 0 | 18 |  | 31121 | -2120 | 27 | 0 | 46681.5 | -3180
[8 empty] | 0 | 0 | 0 | 0
Remove the modern plywood sheathing only to the pendulum gantry and cart away. Allow for temporary edge protections to the gantry following removal. | 3.3 | m | 0
Allow for temporarily removing all electrical conduits and fittings in the external wall elevations in preparation of the internal limewashing. Allow for reinstatement and provide electrical testing upon completion. |  | Item | 0
Second Floor
Carefully remove the existing downpipe and hopper and provide temporary rainwater protections as section C.2 - Roof Repairs. |  | Item | 0
Carefully remove the modern plywood enclosure sheathing, framing and doors, and cart away. Ensure that any remaining clock mechanisms and controls are protected and temporarily relocated before being installed in their final locations. | 4.4 | m | 0
Carefully remove the temporary clear plastic sheeting and battens to the internal side of the belfry louvres and ensure that temporary protections are installed to prevent birds from accessing the internal spaces. | 4 | Nr | 0
Remove the redundant timber battening in the north external elevation. |  | Item | 0
Remove the redundant timber battening in the west external elevation. |  | Item | 0
Remove the redundant timber battening in the south external elevation. |  | Item | 0
Remove the redundant timber battening in the east external elevation. |  | Item | 0
Allow for the removal of all vegetation including roots to all clock embrasures. |  | Item | 0
Carefully remove the temporary modern sterling modern and plastic sheeting in the ceiling zones of the clock face enclosures and in preparation of the new boarded lead weatherings. | 3 | Nr | 0
Allow for temporarily removing all electrical conduits and fittings in the external wall elevations in preparation of the internal plaster repairs. Allow for reinstatement and provide electrical testing upon completion. |  | Item | 0
Specialist Cleaning and Removals
Ground Floor and Internal Stair
Allow for the removal of debris throughout the ground floor areas. |  | Item | 0
Allow for the removal of debris to the internal stairs including the inter-mural stair. |  | Item | 0
First Floor and Clock Gantry
Allow for the removal of debris and guano over modern OSB floor sheathing prior to its removal. |  | Item | 0
Extra over for cleaning horizontal surfaces such as cills, ladder and fixtures to be retained etc. |  | Item | 0
Allow for the removal of debris and guano over the floorboards to the clock gantry. |  | Item | 0
Second Floor
Allow for the removal of debris and guano over floorboards. |  | Item | 0
Extra over for cleaning horizontal surfaces such as cills, ladders and fixtures to be retained etc. |  | Item | 0
Allow for the removal of debris and guano over the clock enclosure joinery.
Allow for the removal of debris, guano and vegetation to the clock embrasures. |  | Item | 0
Ground Floor Flagstone Repairs
Note: The existing floor is currently obscured by stored Employer/ Contractor items and the existing floor will need to be surveyed prior to the commencement of repair. Provisional sums have been included to cover any unknown repairs and careful lifting and rebedding will be required to ensure that the floor is free from any significant trip hazards where the space will come into public use. |  | Item | 0
Note: Allow for liaison with the Architect to undertake inspection of the floor prior to commencement. |  | Item | 0
Removal and Lifting
Allow for inspecting the existing flagstones with the architect prior to removing any of the existing fabric.
Allow for raking out and cleaning joints in preparation of re-grouting the flagstone flooring as the AS. | 15.3 | m² | 0
Allow for carefully lifting a clear route for laying new electrical route below the floor as section C.6 - Electrical Services, rebedding prior to the reinstatement of the existing floor. A suitable route will need to be established on site and identifying areas that will need to be repaired concurrently. Existing flagstones to be lifted and set aside in area where they cannot be damaged. |  | Item | 0
Re-laying and Finishing
Allow the following PROVISIONAL SUM for sourcing and replacing damaged Forest of Dean Pennant flagstones as the AS and allow for rebedding. |  | Item | 2000
Allow for relaying lifted flagstones following the installation of new wiring routes in the floor. |  | Item | 0
Allow for regrouting the existing flagstone flooring as the AS. | 15.3 | m² | 0
Ground Floor Stone Stairs/ Tread Repairs
Note: The existing stone stairs are cantilevered and anchored into the wall on one side with interlocking steps. Each tread acts as a beam and securing the step below. Alterations to the stair will involve the careful and sequenced dismantling to allow for stone replacement and its reconstruction.
Note: The stone mason is to prepare a methodology for safely dismantling and reconstructing and to be approved by the Architect/ Structural Engineer before work commences to repair the stair. |  | Item | 0
Note: There is no easy way to remove ironwork from masonry and the process is likely to cause some damage to the surrounding stone. If possible, remedial work should therefore be carried out in situ using the National Heritage Ironwork Group (NHIG) principles of minimum intervention (see Further Information). The Metalwork Conservator is to provide a detailed and coordinated method statement with the Stonemason prior to the removal of the historic ironwork. |  | Item | 0
South Stair
Carefully dismantle the stair, labelling each stone tread and set aside for reconstruction. Carefully remove the decorative metal handrail and set aside for repair by the Metalwork Conservator. Allow for carefully removing the molten lead pockets from the stone and clean before resecuring the decorative metalwork. Damaged stone sections to be inspected before repairs are carried out and to establish if any of the existing sections can be salvaged for repair. |  | Item | 0
Lightly clean and de-scale the existing treads before reinstatement. |  | Item | 0
Allow for full stone replacement to the damaged tread sections where the stone has split and unsympathetic resin repairs have been carried out. | 2 | Nr | 0
Allow for the full stone replacement of the bottom tread where the riser is severely weathered. Consider stone indent repair if the structural integrity of the stone remains intact. | 1 | Nr | 0
Reset the existing stair allowing for full support as required. |  | Item | 0
North Stair
Carefully remove the decorative metal handrail and set aside for repair by the Metalwork Conservator. Allow for carefully removing the molten lead pockets from the stone and clean before resecuring the decorative metalwork. |  | Item | 0
Lightly clean and de-scale the existing treads in-situ. |  | Item | 0
Carry out an indent repair to the third tread following the removal of the modern rainwater downpipe. |  | Item | 0
Allow the following PROVISIONAL SUM for stone repairs following removal of the ironwork from the masonry, to be confirmed by the Architect and executed by a qualified mason. |  | Item | 1000
Decorative Metalwork Repairs
Note: See the note under the section 'Ground Floor Stone Stairs/ Tread Repairs'. Refer to drawings 1398 (22)01 and (50)02.
Note: The metal conservator is to prepare a methodology for safely removing and reinstating missing sections of the decorative metalwork before work commences to repair the balustrades. |  | Item | 0
South Stair
Allow for careful removal of the existing balustrade, piece in new sections of metal and reinstate the balustrade upon completion of the repairs. Allow for full redecoration and protections as required for the remaining duration of the contract. |  | Item | 0
North Stair
Allow for careful removal of the existing balustrade, piece in new sections of metal and reinstate the balustrade upon completion of the repairs. Allow for full redecoration and protections as required for the remaining duration of the contract. |  | Item | 0
Ground Floor Coffered Ceiling Repairs
Note: Structural Engineer to visit site when decayed timber ends have been cut to the primary beam end repairs, to confirm details and bearing requirements. Ensure that temporary propping is in place.
Note: Temporary propping of the ground floor ceiling structure to be developed by the Main Contractor.
Preparatory Works and Investigations
The Main Contractor is to confirm with the Structural Engineer whether the existing masonry in the external walls is suitable to bear onto. Wall areas to be carefully exposed prior to works proceeding as the removals item below. Allow for pricing new padstones and to be omitted from the Contract sum is suitable bearing is possible. |  | Item | 0
Clean voids around joist bearing ends and all joist ends to be inspected once ceiling access is in place. |  | Item | 0
Removals and Temporary Works
Carefully break out existing masonry areas to a neat finish and recess back from the face of the wall by 100mm. | 4 | Nr | 0
Carefully remove section of decayed timber, not greater than 170mm from the face of the wall and including from within the wall. | 4 | Nr | 0
Allow for carefully removing existing floor joists to locations where new steel angle is to be installed either side of the primary beams and set aside for reuse. | 4 | Nr | 0
Allow for carefully removing modern timber repairs (undersized joists) to the ceiling. | 4 | Nr | 0
Allow for carefully removing rotten timber ceiling joists to the ceiling. | 9 | Nr | 0
Allow for removing existing modern floor joists where alterations in the ceiling are proposed. | 3 | Nr | 0
Carefully remove existing oak moulded ogee profile to the perimeter of the coffered ceiling panels and set aside for reuse. De-nail and lightly clean in preparation of new decoration finishes. | 38 | m | 0
Padstones and Masonry Facings
Allow for new 400(w) x 150(d) x 150(l)mm concrete padstones as the structural engineer's specification to be set back from the wall face. | 4 | Nr | 0
Beam ends to be concreted into wall pocket as the Structural Engineer's drawings and specification, with 50mm concrete cover following the removal of the decayed timber beam ends. | 4 | Nr | 0
Allow for new 100mm rubble Pennant stone facings to be bedded in lime mortar below the primary beams to the north and south elevations, and as the Architect's drawings and AS. | 0.25 | m² | 0
Carpentry Repairs
Fabricate and install new 150 x 75 x 10mm steel angle, fixed either side of the primary beams with 2no. Pairs of M12 bolts at 350m centres. Length to suit agreed bearing locations. | 8 | Nr | 0
Reinstate existing ceiling joists set aside and install new 170 x 50mm C24 joists to be supported on new joist-hangers and steel angle, and fixed using timber blocking skew nailed tight between the joists. |  | Item | 0
Allow for installing new 170 x 50mm C24 joists, end-fixed to primary timbers using joist-hangers as the Structural Engineer's details and drawings, where replacement of undersized joists are required. | 4 | Nr | 0
Install new 170 x 50mm C24 timber joists end-fixed to primary timbers to support the new pendant light fitting. New joists to be supported via joist-hangers to the Structural Engineer's drawings and specification. Install 170 x 50mm C24 timber on its side to be end-fixed via pairs of angle brackets as the Structural Engineer's drawings and specification, to support the pendant light fitting below. |  | Item | 0
Proposed ceiling hatch trimming to comprise 170 x 50mm C24 doubled-up joists where perpendicular to the primary beam and masonry bearing and cut to size where spanning between. Doubled-up joists to be fixed together via 3no. M12 bolts. Joists to be end-fixed to primary beam and masonry wall using joist hangers as the Structural Engineer's drawings and specification. Cut joists to be end-fixed to the doubled-up joists via joist hangers as the Structural Engineer's drawings and specification. |  | Item | 0
Reinstate the existing oak moulded ogee profile to the perimeter edge of the reinstated lath and plaster coffered ceiling panels following the installation of the new plaster work. | 38 | m | 0
Allow for installing new oak moulded ogee profiles to the perimeter edge of the reinstated lath and plaster coffered ceiling panels where missing, and to match the existing profile. | 5.2 | m | 0
Allow the following PROVISIONAL SUM for additional joist end repairs following inspection, to be confirmed by the Architect and executed by a qualified carpenter. |  | Item | 300
Lath and Plaster Ceiling
Allow for supplying and installing new riven oak lath to the underside of the ceiling as the Architect's drawings and AS. | 13.1 | m² | 0
Extra over for the access hatch. | 0.4 | m² | 0
Allow for supplying and installing new lime plaster ceiling as the Architect's drawings and AS. | 13.1 | m² | 0
Extra over for the access hatch. | 0.4 | m² | 0
Internal Upper Floor Repairs
First Floor
Allow for the full replacement of existing floorboards as the Architect's drawings and AS. Existing floorboards to be inspected by the Architect prior to their removal and floorboards to be re-used and conserved wherever possible. | 16.3 | m² | 0
Allow for new pitch pine floorboards or to match the existing where the area of floor is to be reinstated adjacent to the ladder access and electrical riser in the south elevation. | 0.4 | m² | 0
Allow for the preparation of the floorboards to receive new wax finishes as the Architect's drawings and AS. | 16.7 | m² | 0
Clock Gantry
Allow for the preparation of the floorboards to receive new wax finishes as the Architect's drawings and AS. | 2.9 | m² | 0
Second Floor
Allow the following PROVISIONAL SUM for timber repairs to the existing floorboards. |  | Item | 300
Allow for the preparation of the floorboards to receive new wax finishes as the Architect's drawings and AS. | 14.4 | m² | 0
Stone Repairs and Consolidation
Ground Floor
Make good the masonry reveals to the existing nave opening following the removal of the infill in the opening. Allow the following PROVISIONAL SUM for making good to include stone repairs and repointing. |  | Item | 500
Piece in new Forest of Dean sandstone to the base of the east door reveal where it has weathered and to receive new plaster finishes. |  | Item | 0
Inter-mural Stair
Lightly de-frass loose stone and remove decaying limewash to the internal stair walls and ceiling . | 13.4 | m² | 0
First Floor
Piece in new thin sections of Forest of Dean Pennant stone around the 2no. beams in the south internal elevation and repoint in lime mortar. |  | Item | 0
De-frass loose stone and remove the decaying limewash in the internal south elevation as drawing 1398 (22)02. Carry out localised repointing in lime mortar as Z21. | 8.4 | m² | 0
De-frass loose stone and remove the decaying limewash in the internal east elevation as drawing 1398 (22)02. Carry out localised repointing in lime mortar as Z21. | 14.4 | m² | 0
De-frass loose stone and remove the decaying limewash in the internal north elevation as drawing 1398 (22)02. Carry out localised repointing in lime mortar as Z21. | 3.4 | m² | 0
De-frass loose stone and remove the decaying limewash in the internal west elevation as drawing 1398 (22)02. Carry out localised repointing in lime mortar as Z21. | 4.6 | m² | 0
Second Floor
Allow for new 100mm rubble Pennant stone facings to be bedded in lime mortar below the truss tie beams, to the north and south elevations as the Architect's drawings and AS. | 0.25 | m² | 0
Internal Clock Embrasure Repairs
Allow for raking out and repointing the brick reveals in lime mortar to the internal clock dial embrasures |  | Item | 0
Allow the following PROVISIONAL SUM for brick repairs to the clock dial embrasures. |  | Item | 250
Lime Plaster Repairs
Ground Floor Walls
Allow for preparing all internal wall areas and replace damaged or missing oak plaster beads as required and as identified on the Architect's drawings and AS. |  | Item | 0
Allow for preparing and locally repairing the south elevation internal wall locations in lime plaster, ensuring that all surrounding features are adequately protected. | 3.2 | m² | 0
Allow for preparing and locally repairing the north elevation internal wall locations in lime plaster, ensuring that all surrounding features are adequately protected. | 3.4 | m² | 0
Allow for preparing and locally repairing the west elevation internal wall locations in lime plaster, ensuring that all surrounding features are adequately protected. | 2.7 | m² | 0
Second Floor Walls
Allow for preparing all internal wall areas where not covered by a separate item. |  | Item | 0
Allow for preparing and locally repairing the south elevation internal wall locations in lime plaster, ensuring that all surrounding features are adequately protected. | 9.1 | m² | 0
Allow for preparing and locally repairing the east elevation internal wall locations in lime plaster, ensuring that all surrounding features are adequately protected. | 14.1 | m² | 0
Allow for preparing and locally repairing the north elevation internal wall locations in lime plaster, ensuring that all surrounding features are adequately protected. | 8.5 | m² | 0
Allow for preparing and locally repairing the west elevation internal wall locations in lime plaster, ensuring that all surrounding features are adequately protected. | 7.7 | m² | 0
Internal Carpentry Repairs
Note: Structural Engineer to visit site when decayed timber ends have been cut to the roof truss end repairs, to confirm details and bearing requirements. Ensure that temporary propping is in place.
Note: Temporary propping of roof structure to be developed by the Main Contractor.
Preparatory Works and Investigation
The Main Contractor is to confirm with the Structural Engineer whether the existing masonry in the external walls is suitable to bear onto. Wall areas to be carefully exposed prior to works proceeding as the removals item below. Allow for pricing new padstones and to be omitted from the Contract sum is suitable bearing is possible. |  | Item | 0
Removals and Temporary Works
Carefully break out existing masonry areas to a neat finish and recess back from the face of the wall by 100mm. | 4 | Nr | 0
Carefully remove decayed wall plates in the north and south external walls. | 2 | Nr | 0
Allow for carefully cutting out the decayed rafter ends to 50% of rafters. |  | Item | 0
Cut off the decayed timber ends to the roof trusses and replace with packing timbers between the new steel. | 4 | Nr | 0
Allow for temporarily removing access hatch connecting timber between the trusses to allow installation of new steelwork. |  | Item | 0
Padstones and Masonry Facings
Allow for new 400(w) x 150(d) x 150(l)mm concrete padstones as the structural engineer's specification to be set back from the wall face. | 4 | Nr | 0
Allow for new 100mm rubble Pennant stone facings to be bedded in lime mortar as the Architect's drawings and AS. | 0.25 | m² | 0
Roof Carpentry Repairs
New ex.120 x 60mm well seasoned oak wall plate to be installed and fixed down with 12mm diameter stainless steel threaded bars at 1200mm crs. and 300mm embedment depth. | 7.7 | m | 0
Allow for fabricating and installing 150 x 75mm PFC bolted either side of the timber truss using M12 bolts as set out on the Structural Engineer's drawings. Length to suit site dimensions and to be welded to the principal rafter steel plates. | 8 | Nr | 0
Allow for fabricating and installing 10mm thick steel plate, welded to PFC on both sides. Allow for well seasoned oak packing timber between the principal rafter and fixed using M12 bolts as the Structural Engineer's drawings and specifications. | 8 | Nr | 0
Existing access hatch connecting timber to be refixed to the truss and tek-screwed to new splice plate. |  | Item | 0
Allow for splice repairs to 50% of the rafter ends using well seasoned oak with sizes to match the existing (ex.120 x 60mm). New rafters to be fixed to existing using 2no. M12 bolts and skew nailed to new wall plate. |  | Item | 0
Wood Beetle Damage Repairs
Note: Allow for the replacement, removal and cutting out of all infected areas where repairs have been identified. The approach to be adopted will assume improved ventilation to the tower and dryer internal conditions following the repair of the building. |  | Item | 0
First Floor
Allow for replacing damaged ceiling joists (ex.110 x 60mm) using well seasoned oak to match the existing and to be bedded into the external wall and notched into the primary beam. | 2 | Nr | 0
Neatly cut out and splice in new sections of timber with 2no. M12 bolts. | 2 | Nr | 0
Second Floor
Neatly cut out and splice in new section of well seasoned oak timber to the truss using M12 bolts. | 1 | Nr | 0
Other Works
Allow the following PROVISIONAL SUM for additional carpentry repairs throughout, to be confirmed by the Architect and executed by a qualified carpenter. |  | Item | 500
Internal Joinery Repairs and Bird Guarding to the Belfry Louvres
Clock Face Enclosures
3nr. Clock face enclosures to be fully repaired to include new ironmongery as the Architect's drawings and AS. To include new boarded roof to receive code 6 lead roof to provide a tray for wind driven rain and protect the joinery below. | 3 | Nr | 0
Bird Guarding
Allow for supply and installation of 4nr. bird guards as the Architect's drawings and AS to the belfry louvres to prevent birds accessing the tower. |  | Item | 0
New Internal Doors and Hatches
Inter-mural Stair Vestibule Door.
Supply and install new oak plank and boarded door as drawing 1398 (50)01 and specification L20 with wax oil finish to be applied on both sides. |  | Item | 0
Allow the following PROVISIONAL SUM for new ironmongery to the internal door. |  | Item | 350
Exterior Hatch - East Elevation
Supply and install new oak plank and boarded door as drawing 1398 (50)01 and specification L20 with exterior wax oil finish to be applied on both sides. |  | Item | 0
Allow the following PROVISIONAL SUM for new ironmongery to the internal door. |  | Item | 350
New Joinery
Incoming Services Riser and Cupboard - CGF.01
Allow for the manufacture and installation of new purpose made joinery as drawing 1398 (50)03 and specification N10, to include all ironmongery and decorative finishes. |  | Item | 0
Decorations and Finishes
Ground Floor Walls
Overhaul the existing timber entrance doors and redecorate as the AS. |  | Item | 0
Allow for preparing all wall areas, removing decayed limewash finishes as required where not covered by a separate item. |  | Item | 0
Allow for preparing and limewashing the south elevation lime plaster wall areas, ensuring that all surrounding features are adequately protected. | 20 | m² | 0
Allow for preparing and limewashing the east elevation lime plaster wall areas, ensuring that all surrounding features are adequately protected. | 9.5 | m² | 0
Allow for preparing and limewashing the north elevation lime plaster wall areas, ensuring that all surrounding features are adequately protected. | 20.5 | m² | 0
Allow for preparing and limewashing the west elevation lime plaster wall areas, ensuring that all surrounding features are adequately protected. | 17.5 | m² | 0
Ground Floor Ceiling
Allow for preparing and limewashing the visible coffered ceiling panels and timber joinery, ensuring that all surrounding features are adequately protected. | 15.3 | m² | 0
South Stair Vestibule Walls and Ceiling
Allow for preparing all wall areas, removing decayed limewash finishes as required where not covered by a separate item. |  | Item | 0
Allow for preparing and limewashing the stair vestibule walls and vaulted ceiling, ensuring that all surrounding features are adequately protected. | 4 | m² | 0
North Stair Vestibule Walls and Ceiling
Allow for preparing all wall areas, removing decayed limewash finishes as required where not covered by a separate item. |  | Item | 0
Allow for preparing and limewashing the stair vestibule walls and vaulted ceiling, ensuring that all surrounding features are adequately protected. | 5 | m² | 0
First Floor Walls
Allow for preparing all wall areas, removing decayed limewash finishes as required where not covered by a separate item. |  | Item | 0
Allow for preparing and limewashing the south elevation rubble stone wall areas, ensuring that all surrounding features are adequately protected. | 21 | m² | 0
Allow for preparing and limewashing the east elevation rubble stone wall areas, ensuring that all surrounding features are adequately protected. | 21.8 | m² | 0
Allow for preparing and limewashing the north elevation rubble stone wall areas, ensuring that all surrounding features are adequately protected. | 19.7 | m² | 0
Allow for preparing and limewashing the west elevation rubble stone wall areas, ensuring that all surrounding features are adequately protected. | 19.5 | m² | 0
Second Floor Walls
Allow for preparing all wall areas, removing decayed limewash finishes as required where not covered by a separate item. |  | Item | 0
Allow for preparing and limewashing the south elevation lime plaster wall areas, ensuring that all surrounding features are adequately protected. | 10 | m² | 0
Allow for preparing and limewashing the east elevation lime plaster wall areas, ensuring that all surrounding features are adequately protected. | 13.1 | m² | 0
Allow for preparing and limewashing the north elevation lime plaster wall areas, ensuring that all surrounding features are adequately protected. | 10 | m² | 0
Allow for preparing and limewashing the west elevation lime plaster wall areas, ensuring that all surrounding features are adequately protected. | 12.2 | m² | 0
Miscellaneous
Ground Floor
Allow the following PROVISIONAL SUM for new foundations and works in connection with the installation of the new timber studwork in the nave opening. |  | Item | 800
C20 timber stud wall to be installed in the reinstated nave opening to the ground floor, to provide a temporary fixing for the War Memorial. New wall to comprise 13mm vertical bead and butt oak t&g boards, on 50 x 25m SW treated timber battens, VCL on 140 x 38mm CLS timber studs at 600mm c/c and full fill mineral wool insulation between the studs, on 9mm OSB sheathing with breather membrane, 50 x 50mm SW treated timber battens to provide ventilation, 18mm external grade WBP plywood to carry the War Memorial. DPC to be installed at the base and reveals and interior timber boards to be limewashed to match adjoining wall surfaces. |  | Item | 0
First Floor
De-rust 3no. exposed metal cramp ends in the east elevation wall over the inter-mural stair and provide paint protection using a rust inhibitor as M60. |  | Item | 0
Clock Gantry
Reclad existing gantry studwork using 13mm vertical bead and butt oak t&g boards with noggins installed every 1.2m vertical centres between the studs. |  | Item | 0
To Main Summary £ |  |  | 6350

## C.5 - Safety Equipment
SECTION C.5 - SAFETY EQUIPMENT
Notes
This section involves the CDP item for designing and installing the safety access improvements to the external roof area.
All work to be undertaken as detailed on the drawings and to the Architect's Specification (shortened to AS in the descriptions below).
The Main Contractor is to ascertain the nature of the works as part of their tender submission to ensure that all of the safety access requirements are understood. | Item | 0
Generally
Liaise with the Architect and allow for their attendance whilst meeting and briefing the specialist sub-contractor. | Item | 0
Completion of Design
Complete Design of Access and Safety Equipment
Refer to drawing 1398 (10)02 showing areas where fall arrest harness and lifeline access is require as NBS Specification N25.
i) The outline design defined in this section and on the drawings is indicative. The appointed contractor is responsible for developing the detailed design requirements in accordance with these documents and the current Work at Height Regulations 2005. | Item | 0
ii) Installation: The designer shall be a 'Registered Competent Person' with an appropriate body such and as recognised by the HSE or equivalent. | Item | 0
iii) Testing: Inspection and testing in accordance with procedures in the latest version of BS 795, BS EN 365 and BS 7883. | Item | 0
iv) Certification: The installer shall supply a copy of the test certificate to the Employer immediately after completion and use with a certificate of conformity issued to the CA. | Item | 0
Proposed Arrangements to the Roof
Allow for installing to the existing galvanised steel gantry system to include a high load start/end post upon access to the roof from the existing roof hatch; intermediate posts with intermediate supports; high load corners, rope grab and lanyard sets as specification N25. | Item | 0
To Main Summary £ |  | 0

## C.6 - Electrical Services
SECTION C.6 - ELECTRICAL SERVICES
Notes
This section involves the CDP item for installing new electrical items to the internal ground and first floor areas.
All work to be undertaken as detailed on the drawings and to the Architect's Specification (shortened to AS in the descriptions below).
Generally
Liaise with the Architect and allow for their attendance whilst inspecting and confirming wiring routes throughout. | Item | 0
In all removals, unless otherwise described, removal is to include all fixings, electrical wiring, containment, fixtures and fittings. In all removals the electrical items are to be retained for client use unless otherwise instructed to remove to an approved disposal point away from the site. | Item | 0
The new wiring routes are to be taken below ground where lighting is proposed in the ground floor. Allow for lifting existing floor slabs on the ground floor and rebedding as Section C.4. Recessed lighting in the ground floor is to be installed in new floor slabs only. Wiring routes for the internal stair and first floor is to be undertaken through the new services cupboard and carried through the first floor ceiling void. | Item | 0
Allow for isolating and disconnecting all electricity and power to the building whilst new electrical installations are being installed. | Item | 0
The Contractor is to be aware that in working within an existing building the previous use of hazardous materials may be encountered, such as asbestos. The Contractor is to maintain awareness of such possibility and fully acquaint themselves with the health and safety information and ensure all appropriate precautions are taken in undertaking the proposed repairs. | Item | 0
Completion of Design
Complete Design of Electrical Services
Refer to drawings 1398 (10)02 and 1398 (13)01, and the Luminaries Schedule.
i) The outline design defined in this section and on the drawings is indicative. The appointed electrical contractor is responsible for developing the detailed design in accordance with these documents and the current IEE Regulations. | Item | 0
ii) Installation: The electrical installer shall be a 'Registered Competent Person' with an appropriate body such as NICEIC or equivalent. | Item | 0
iii) Testing: Inspection and testing in accordance with procedures in the latest version of BS 7671. | Item | 0
iv) Certification: The installer shall supply a copy of the test certificate to the Employer within 14 days of completion. The installer shall also give a copy of the certificate to the Building Control Officer. | Item | 0
v) Unless otherwise noted, all wiring to be concealed within structural voids and not surface mounted. Details and methodology to be agreed with the Architect before proceeding. | Item | 0
vi) All new electrical wiring to be to FP200 throughout to minimise any potential risk against fire. Armoured cables to be used below ground to prevent extreme mechanical stress and moisture damage. | Item | 0
vii) Generally, all electrical accessories to be flush mounted. | Item | 0
Mains Supply
i) Mains supply: The existing incoming supply shall be retained and reused. It is assumed this supply is at least 18kVA in capacity. The Main Contractor shall determine the requirements as part of their tender submission. | Item | 0
Install New Electrical Distribution Board in Services Cupboard CGF.01:
i) Install new distribution board including MCB and RCBO protection. | Item | 0
ii) Connect all circuits. | Item | 0
iii) Provide sufficient circuits for: | Item | 0
All new circuits for the proposed interior works.
Sufficient extra circuits for future development works.
DB to be Schneider Isobar P 125 18 Way with integral switch disconnector or similar.
Power
Install New Power and Interior Lighting Circuits
i) Run new lighting circuits to outlets as shown on drawings 1398 (10)02 and 1398 (13)01. All cables to be concealed behind wall/ ceiling finishes: | Item | 0
General 13amp internal lighting circuit.
Install New Socket/ Spur Power Outlet Accessories
i) Install 8nr new double switched outdoor commando sockets to BS EN 60309-2 in positions as shown on drawing 1398 (10)02 to the parapet wall in the tower, including stainless steel conduit for external use. Proposals and layout to be agreed with the Architect before installing and allow for suitable flashing detail where the power will need to pass through the roof. | Item | 0
Interior Lighting
Strip Out Existing Lighting Circuits (Excluding Emergency Lighting System)
i) Remove all existing circuits and accessories except any emergency lighting components. | Item | 0
ii) Retain and protect emergency lighting system cables and fittings. | Item | 0
Install New Interior Lighting Circuit
i) Install new lighting circuits with outlets as located on drawings. | Item | 0
Install New Interior Light Switch Controls
i) Install new lighting accessories from MK 'Logic Plus' range by MK Electric, unless otherwise noted. Lighting accessories to be installed in the riser cupboard and not to be publicly visible. | Item | 0
Finish: white plastic.
Install New Interior Light Fittings
Install new lighting as the Luminaries Schedule and drawings. | Item | 0
Fittings shall be dimmable, complete with compatible dimmer switch/ control. | Item | 0
Exterior Lighting
Replace 4no. exterior recessed light fittings to the landscaped areas at the base of the tower, removing all existing exterior circuits and install new lighting circuits with controls in the ground floor services cupboard. Lighting to be controlled via an automatic and programmable timer. Controls to allow automatic switching for dawn / dusk and with manual override. Manufacturer to be as Contractor's proposals and compatible with the existing exterior provisions. | Item | 0
BWIC Installations
Allow the following PROVISIONAL SUM for BWIC with all electrical installations, above that already covered in the schedule and drawings. |  | 1000
To Main Summary £ |  | 1000

## D - Dayworks
SECTION D - DAYWORKS
General
Charges for work valued on a daywork basis will be calculated in accordance with Sections (3), (4) and (5) of the Definition of Prime Cost of Daywork published by the Royal Institution of Chartered Surveyors and National Federation of Building Trades Employers, current at the date of tender. The individual rates for plant shall be at local plant hire rates. The percentage additions required by the Contractor for incidental costs overheads and profit as defined in Section (6) of the Definition of Prime Cost of Day work are to be included within the " all-in" rates applied to the Provisional No. of hour assessments for Labour - thus the rates inserted will be deemed to cover the total cost of employing labour for an hour undertaking specific tasks of work; i.e. NOT including meal breaks, wash up and cleaning up time, etc.
In the case of plant and materials the percentage additions required are to be inserted below the Provisional Sums hereinafter and these percentages will be use in the calculation of the cost of work valued on a daywork basis.
In general, variations will be measured pro rata scheduled rates or by "fair valuation" methods; only where work cannot be properly measured and valued will the Contractor be allowed daywork rates at the rates set out below.
Duplicate copies of vouchers specifying the times daily spent upon the work, the worker's names and the materials employed are to be delivered for verification to the Architect or their authorised representative not later than the end of the week following that in which the work has been executed. All vouchers recording the labour are to state ages for apprentices 16-20 years olds and for labourers 16-18 years old in addition to the usual names and trades.
Detailed calculation of the prime cost of labour for each class of workman and according to the time when the daywork is executed are to be submitted by the Contractor for agreement.
The Contractor is to supply evidence of such charges at the time of agreeing costs.
Labour
Slate Roofer | 10 | Hrs | 0 | 0
Leadworker | 15 | Hrs | 0 | 0
Mason | 50 | Hrs | 0 | 0
Carpenter | 35 | Hrs | 0 | 0
General Labourer | 50 | Hrs | 0 | 0
Materials
Provide the NETT PROVISIONAL SUM of £2,500.00 for Prime cost of Materials used in Daywork | Item |  |  | 2500
Add for incidental costs and profit (the contractor is to insert the percentage required and extend the amount into the money column) | 0 | % |  | 0
Plant
Provide the NETT PROVISIONAL SUM of £2,500.00 for Prime Cost of Plant used in Daywork |  |  |  | 2500
Add for incidental cost and profit (ditto as above) | 0 | % |  | 0
To Main Summary £ |  |  |  | 5000

## F - Main Summary
SECTION F - MAIN SUMMARY
Priced Sections |  | Labour | Mats | Subbie | Prov | Labour
31.38
Section A - Preliminaries | 50544 |  |  |  | 50544
Section B - Temporary Works | 1800 | 564.84 | 0 | 48868.6 | 2880 | 18 | hrs for 1
Section C.1 - External Repairs | 3600 | #REF! | #REF! | #REF! | #REF! | #REF! | hrs for 1
Section C.2 - Roof Repairs | 5150 | #REF! | #REF! | #REF! | #REF! | #REF! | hrs for 1
Section C.3 - External Alterations | 1800 | #REF! | #REF! | #REF! | #REF! | #REF! | hrs for 1
Section C.4 - Internal Alterations and Repairs | 6350 | #REF! | #REF! | #REF! | #REF! | #REF! | hrs for 1
Section C.5 - Safety Equipment | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | hrs for 1
Section C.6 - Electrical Services | 1000
Section D - Dayworks | 5000 |  |  |  | 5000 | 0 | hrs for 1
Total
Total (Excluding VAT) £ | 75244